## Guidance
General guidance regarding the facility renewal program
In general, any required facility renewal scope should be included in remodel project budgets.
In other words, FRP funds will not be used to augment remodel project budgets.
Occasionally, facility renewal projects by nature of their scope and / or cost will not meet the capitalization threshold.
In these cases, the project manager needs to work with BOC Finance and the appropriate CBO as soon as possible to discuss project timing.
Capital projects impact a school's balance sheet and generally span multiple fiscal years.
Operating projects impact a school's income statement, which is reported on quarterly through variance reporting.
Due to the timing of when fiscal year budgets are approved, opex facility renewal project(s) may not be included in the school's budget.
When this is the case, the school will need to explain the negative impact of the opex facility renewal project(s) on their income statement.

## Summary_for Web-1
Facility Renewal Program: Summary by School
Last updated: | 2026-01-14
School | GSF | FY23 - FY26 Cumulative Contribution | FY23 Funded Projects | FY24 Funded Projects | FY25 Funded Projects | FY26 Funded Projects | Contribution vs. Funded
Arts & Science | 1168519.772 | 18052948.496 | 2276289.625 | 2619344.704 | 2109671.35 | -2253.29 | 11049896.107
Blair | 121417.211 | 2048063.4197 | 574290 | 1916810 | 1486000 | 1567758.28 | -3496794.8603
College of Connected Computing | 42638.0889 | 193576.9234 | 0 | 0 | 0 | 25550 | 168026.9234
Divinity | 58286.9615 | 957401.8089 | 96362.5 | 3660360 | 304500 | 2369000 | -5472820.6911
Engineering | 490439.8851 | 8742210.2724 | 353000 | 24933 | 3324484.74 | 424238.84 | 4615553.6924
Law | 119265.3553 | 1969283.7761 | 1206134.5 | 661160 | 284467.3 | -120332 | -62146.0239
School of Medicine | 334042.3631 | 4958227.8835 | 1036871.875 | -17509.674 | 1016425.05 | 309738 | 2612702.6325
School of Nursing | 105746.45 | 1741672.2044 | 4900 | 286527 | 45530 | -64230.19 | 1468945.3944
Owen | 99610.0673 | 1499019.2091 | 300000 | 1576500 | 1600000 | -222611.86 | -1754868.9309
Peabody | 381580.0251 | 6352482.4122 | 2949437.76 | 600347.91 | 0 | -161709.56 | 2964406.3022
| 2921546.1792 | 46514886.4056 | 8797286.26 | 11328472.94 | 10171078.44 | 4125148.22 | 12092900.5456
Estimated funded projects is anticipated funding to be transferred back to the school for approved FRP projects from FRP program funds.

## Summary_for Web-2
Facility Renewal Program: Summary by Project
| Last updated: | 2026-01-14
| Projects |  |  |  | (1) | (2) | (2) | (2) | (2)
| Project Status | eBuilder Proj No | School | Project Description | Estimated Total Budget | FY23 FRP Funding | FY24 FRP Funding | FY25 FRP Funding | FY26 FRP Funding
1 | Complete | 10085 | Peabody | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 17500 | 0 | 0 | 0
2 | Complete | 10098 | School of Medicine | MRB III - 4th Floor - Replace Controls (Phase 2) | 1212084.54 | 1216485.5 | -4400.96 | 0 | 0
3 | Complete | 10146 | School of Nursing | Godchaux Hall - HVAC Upgrade | 196626.81 | 4900 | 255957 | 0 | -64230.19
4 | Complete | 20179 | Law | Law School - Fire Alarm System Replacement | 629728.64 | 722694.5 | 0 | -92965.86 | 0
5 | Complete | 20336 | Blair | Blair School of Music - Elevator #3 Modernization | 280600 | 327890 | -47290 | 0 | 0
6 | Active | 20431 | Divinity | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | 3800000 | 69862.5 | 3660360 | 0 | 0
7 | Active | 20478 | Arts & Science | Bryan Building - Swing Space Renovation - A&S Planning | 2790000 | 81100 | 1028900 | 0 | 0
8 | Active | 20489 | Divinity | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | 3600000 | 26500 | 0 | 304500 | 2369000
9 | Complete | 20497 | Peabody | Jesup - Roof Replacement | 34565.5 | 79415.5 | -44850 | 0 | 0
10 | Complete | 20506 | Peabody | Wyatt Center - Window Replacement | 307776.26 | 344155.26 | -36379 | 0 | 0
11 | Deferred / On Hold | 20560 | Law | Law School - Electrical Gear Replacement - FY23 FR | 905610 | 0 | 0 | 0 | 0
12 | Complete | 20562 | Peabody | Wyatt Center - VAV Replacement | 362559.64 | 405791 | -43231.36 | 0 | 0
13 | Deferred / On Hold | 20563 | Engineering | Keck FEL - Roof Replacement | 386000 | 0 | 0 | 0 | 0
14 | Complete | 20566 | Arts & Science | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | 722586.68 | 781870 | -59283.32 | 0 | 0
15 | Complete | 20573 | Peabody | Wyatt Center - Roof Replacement | 1113460 | 1232681 | -119221 | 0 | 0
16 | Complete | 20574 | School of Medicine | MRB III - Steam Coil Replacement | 195665 | 218202 | -22537 | 0 | 0
17 | Active | 20577 | Blair | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | 1300000 | 223000 | 0 | 1077000 | 0
18 | Complete | 20644 | Peabody | Peabody Administration - Envelope Repairs | 571789 | 630554 | -58765 | 0 | 0
19 | Complete | 20645 | Arts & Science | Benson Old Central - Replace Soffit and Doors | 114350 | 125875 | -11525 | 0 | 0
20 | Active | 20667 | Engineering | 1025 16th Avenue - Mechanical and Electrical Upgrades | 1550000 | 146500 | 0 | 1398860 | 0
21 | Active | 20668 | Engineering | Keck FEL - Mechanical Upgrades | 3960000 | 206500 | 24933 | 0 | 0
22 | Complete | 20698 | Arts & Science | Wilson Hall - Fire Alarm Replacement | 586776.36 | 29250 | 649263 | 0 | -91736.64
23 | Complete | 20700 | Arts & Science | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | 85577 | 79623 | 5954 | 0 | 0
24 | Complete | 20701 | Arts & Science | SC-5 - Chemical Discharge Replacement | 447535.86 | 499093 | 0 | 0 | -51557.14
25 | Complete | 20702 | Peabody | Wyatt Center - Elevator #2 Modernization | 209419 | 239341 | -29922 | 0 | 0
26 | Complete | 20718 | Arts & Science | Buttrick Hall - 3rd Floor Inequality Renovations | 96166 | 96166 | 0 | 0 | 0
27 | Active | 20723 | School of Medicine | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | 1610000 | 160500 | 0 | 1539500 | 0
28 | Active | 20724 | Blair | Blair School of Music - Steam Line - FY 23 | 1987500 | 23400 | 1964100 | 0 | -148241.72
29 | Complete | 20735 | Owen | Owen - Roof Replacement (Third Level) | 276500 | 300000 | -23500 | 0 | 0
30 | Active | 20767 | Peabody | Six Magnolia Circle - Foundation Repairs | 149000 | 0 | 148299 | 0 | 0
31 | Complete | 20771 | Arts & Science | SC4 - Interstitial Space HVAC Modifications | 17972 | 24997 | -7025 | 0 | 0
32 | Complete | 20772 | Owen | OGSM Old Mechanical- Slate Roof & Window Replacement | 2977388.14 | 0 | 1600000 | 1600000 | -222611.86
33 | Complete | 20792 | Law | Law School - Sections 1, 2, & 3 Roof Replacement | 450775 | 483440 | -32665 | 0 | 0
34 | Complete | 20811 | Peabody | One Magnolia Circle - Retaining Wall Repair | 123523.71 | 0 | 285233.27 | 0 | -161709.56
35 | Active | 20812 | Engineering | 1025 16th Avenue - Patio Repairs | 485000 | 0 | 0 | 486135 | 0
36 | Complete | 20831 | Arts & Science | SC6 - HVAC Upgrades - Feasibility Study | 24000 | 0 | 24000 | 0 | 0
37 | Complete | 20832 | Arts & Science | Wilson Hall - HVAC Replacement | 24000 | 0 | 24000 | 0 | 0
38 | Complete | 20833 | Arts & Science | SC5 - HVAC Replacement (Design Services) | 24000 | 0 | 24000 | 0 | 0
39 | Active | 20857 | Peabody | One Magnolia Circle - Elevator Modernization | 499184 | 0 | 499184 | 0 | 0
40 | Complete | 20884 | Law | Law School - Exterior Window Painting | 480318 | 0 | 675650 | 0 | -195332
41 | Active | 20885 | Arts & Science | NMR - Replace Air Compressors | 130000 | 0 | 113053.4 | 30000 | -19309.51
42 | Complete | 20911 | Arts & Science | Buttrick Hall - Elevator Upgrades | 54613 | 0 | 61045 | 0 | -6432
43 | Active | 20912 | Arts & Science | Benson Hall - Elevator Upgrades | 59798 | 0 | 59798 | 0 | 0
44 | Active | 20913 | Arts & Science | Wilson Hall - Elevator Upgrades | 96612 | 0 | 96612 | 0 | 0
45 | Active | 20922 | Arts & Science | Vaughn Home - Exterior Improvements | 170000 | 0 | 197150 | 0 | 0
46 | Complete | 20924 | School of Nursing | Frist Hall - Stairwell Roof Replacement | 24500 | 0 | 30570 | -6070 | 0
47 | Active | 20925 | Blair | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | 2125000 | 0 | 0 | 409000 | 1716000
48 | Active | 20936 | Arts & Science | Wilson Hall - Lighting Retrofit for 103 and 126 | 405000 | 0 | 404655.91 | 0 | 0
49 | Active | 20940 | Engineering | 1025 16th Avenue - Security System Replacement | 310000 | 0 | 0 | 309548.64 | 0
50 | Complete | 20945 | Other | Seigenthaler Building - HVAC Improvements | 70200 | 0 | 99000 | 0 | -28800
51 | Active | 20958 | Arts & Science | Furman Hall - Elevator Modernization | 290000 | 0 | 18175 | 243454 | 0
52 | Active | 20962 | Arts & Science | Vaughn Home - Roof Replacement | 1750000 | 0 | 0 | 1800 | 0
53 | Active | 20979 | Engineering | 1025 16th Avenue - Roof Replacement | 270000 | 0 | 0 | 529750 | 51438
54 | Active | 20982 | Law | Law School - Elevator 1 Modernization | 272000 | 0 | 18175 | 253825 | 0
55 | Active | 20984 | Arts & Science | Wilson Hall - 1st Floor Urinal Replacement | 167000 | 0 | 0 | 167000 | 0
56 | Active | 21004 | Arts & Science | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | 940000 | 0 | 0 | 992453 | 0
57 | Deferred / On Hold | 21005 | Arts & Science | SC5 - HVAC Upgrade Floors 4, 5, and 7 (Phase 2) | 0 | 0 | 0 | 0 | 0
58 | Deferred / On Hold | 21006 | Engineering | SC5 - HVAC Upgrade Floors 3 and 6 (Phase 3) | 0 | 0 | 0 | 0 | 0
59 | Deferred / On Hold | 21007 | Engineering | SC5 - HVAC Upgrade Floors 8 and 9 (Phase 4) | 0 | 0 | 0 | 0 | 0
60 | Active | 21010 | Engineering | Featheringill-Jacobs Hall - Hot Water Tank Replacement | 125000 | 0 | 0 | 126024 | -13199.16
61 | Active | 21035 | Law | Law School - Roof Ladders | 50000 | 0 | 0 | 36108.16 | 0
62 | Active | 21051 | School of Medicine | MRBIII - 5th Floor Controls | 0 | 0 | 0 | 0 | 27500
63 | Active | 21066 | Arts & Science | SC2 - MEP Feasibility Study | 29160 | 0 | 0 | 29160 | 0
64 | Active | 21067 | School of Nursing | Godchaux Hall - Phase 2 HVAC Upgrades and Roof Replacement | 2500000 | 0 | 0 | 46600 | 0
65 | Active | 21068 | Arts & Science | Buttrick Hall - Insulate First Floor Slab | 0 | 0 | 0 | 34837.4 | 0
66 | Active | 21070 | Engineering | Olin Hall - Exterior Facade Cleaning | 848722 | 0 | 0 | 392042.1 | 0
67 | Active | 21071 | Arts & Science | SC1 - MEP Feasibility Study | 19440 | 0 | 0 | 19440 | 0
68 | Deferred / On Hold | 21072 | Arts & Science | Calhoun Hall - MEP Feasibility Study | 10000 | 0 | 0 | 0 | 0
69 | Deferred / On Hold | 21073 | Arts & Science | Furman Hall - MEP Feasibility Study | 10000 | 0 | 0 | 0 | 0
70 | Deferred / On Hold | 21074 | Law | Law School - MEP Feasibility Study | 10000 | 0 | 0 | 0 | 0
71 | Active | 21094 | Law | Godchaux Hall - Replace Fire Pump | 87500 | 0 | 0 | 87500 | 0
72 | Complete | 21108 | School of Nursing | 1025 16th Avenue - Electrical and HVAC Study | 5000 | 0 | 0 | 5000 | 0
73 | Active | 21113 | Engineering | MRBIII - Lecture Hall V1220 Lighting Upgrade | 85000 | 0 | 0 | 82125 | 0
74 | Active | 21114 | School of Medicine | MRBIII - Chemical Discharge Tank Replacement | 70000 | 0 | 0 | 68452 | 0
75 | Active | 21127 | School of Medicine | MRBIII - Cooling Tower Overhaul | 450000 | 0 | 0 | 0 | 449020
76 | Active | 21155 | Arts & Science | SC2 Restroom Upgrades | 750000 | 0 | 0 | 0 | 0
77 | Active | 21156 | Engineering | Olin Hall 2nd Floor Chiller | 500000 | 0 | 0 | 0 | 386000
78 | Active | 21157 | Arts & Science | Cohen Memorial - Water Intrusion Repair | 250000 | 0 | 0 | 0 | 0
79 | Active | 21165 | Peabody | Wyatt Center Rotunda Repairs | 0 | 0 | 0 | 0 | 0
80 | Active | 21173 | College of Connected Computing | 17th & Horton Elevators Modernization | 575000 | 0 | 0 | 0 | 25550
81 | Active | 21174 | Arts & Science | Buttrick Hall - Restore / Replace Exterior Wood Doors and Closures | 0 | 0 | 0 | 0 | 0
82 | Active | 21175 | Arts & Science | Law School Partial Roof Replacement | 0 | 0 | 0 | 0 | 0
83 | Active | 21176 | Law | Law School Walkway Replacement | 160000 | 0 | 0 | 0 | 0
84 | Active | 21177 | Arts & Science | SC2 Molecular Biology HVAC Replacement | 2215000 | 0 | 0 | 0 | 0
85 | Active | 21178 | Law | Law School - Air Compressor Replacement #6 | 30000 | 0 | 0 | 0 | 75000
86 | Active | 21189 | Blair | Blair School Legacy VAV Replacement and Duct Encapsulation | 800000 | 0 | 0 | 0 | 0
87 | Active | 21198 | Arts & Science | SC7 - AHUs Replacement | 1300000 | 0 | 0 | 0 | 0
[5 empty] | 52620082.14 | 8797286.26 | 11427472.94 | 10171078.44 | 4096348.22
(1) Estimated total budget represents the best rough order of magnitude for total project costs for project status Active and Deferred / On Hold. For completed project status, final projects costs are shown.
(2) FYxx FRP funding indicates anticipated funding to be transferred back to the school for approved FRP projects from FRP program funds.

## Contributions
Facility Renewal Program: Contributions - FY23 |  |  | Facility Renewal Program: Contributions - FY24 |  |  | Facility Renewal Program: Contributions - FY25 |  |  | Facility Renewal Program: Contributions - FY26 |  |  | Facility Renewal Program: Contributions - FY27
|  | 3.41 |  |  | 3.97 |  |  | 4.54 |  |  | 4.54 |  |  | 4.54
School | GSF | Contribution | School | GSF | Contribution | School | GSF | Contribution | School | GSF | Contribution | School | GSF | Contribution
Arts & Science | 1075461.7321 | 3663826 | Arts & Science | 1059147 | 4204813.59 | Arts & Science | 1074720.0751 | 4879229.141 | Arts & Science | 1168519.772 | 5305079.765 | Arts & Science | 1077626.6351 | 4892424.9236
Blair | 121421.4269 | 413652 | Blair | 121421 | 482041.37 | Blair | 132408.7911 | 601135.9118 | Blair | 121417.211 | 551234.1379 | Blair | 121400.0491 | 551156.2229
College of Connected Computing | 0 | 0 | College of Connected Computing | 0 | 0 | College of Connected Computing | 0 | 0 | College of Connected Computing | 42638.0889 | 193576.9234 | College of Connected Computing | 46868.4522 | 212782.7731
Divinity | 57814.7309 | 196960 | Divinity | 58263 | 231304.11 | Divinity | 58263.1925 | 264514.8938 | Divinity | 58286.9615 | 264622.8051 | Divinity | 58286.9615 | 264622.8051
Engineering | 537962.3327 | 1832701 | Engineering | 552478 | 2193337.66 | Engineering | 548364.4349 | 2489574.5343 | Engineering | 490439.8851 | 2226597.0781 | Engineering | 492817.6966 | 2237392.3424
Law | 120155.4846 | 409339 | Law | 120155 | 477015.35 | Law | 119265.3553 | 541464.7131 | Law | 119265.3553 | 541464.7131 | Law | 119553.8956 | 542774.6861
School of Medicine | 280022.3999 | 953965 | School of Medicine | 265674 | 1054725.78 | School of Medicine | 315635.413 | 1432984.7751 | School of Medicine | 334042.3631 | 1516552.3283 | School of Medicine | 325737.1176 | 1478846.5141
School of Nursing | 106166.7 | 361683 | School of Nursing | 105746 | 419811.62 | School of Nursing | 105746.41 | 480088.7014 | School of Nursing | 105746.45 | 480088.883 | School of Nursing | 105746.45 | 480088.883
Owen | 59008.3617 | 201027 | Owen | 99140 | 393585.8 | Owen | 99598.3928 | 452176.7035 | Owen | 99610.0673 | 452229.7056 | Owen | 99610.0673 | 452229.7056
Peabody | 390796.8848 | 1331346 | Peabody | 396133 | 1572648.01 | Peabody | 377998.9181 | 1716115.0883 | Peabody | 381580.0251 | 1732373.3138 | Peabody | 469092.8936 | 2129681.737
| 2748810.0535 | 9364499 |  | 2778157 | 11029283.29 |  | 2832000.9829 | 12857284.4623 |  | 2921546.1792 | 13263819.6534 |  | 2916740.2187 | 13242000.5927
Contribution |  | 9364499 | Contribution |  | 11029283.29 | Contribution |  | 12857284.4623 | Contribution |  | 13263819.6534 | Contribution |  | 13242000.5927
Anticipated spend |  | 8797286.26 | Anticipated spend |  | 11427472.94 | Anticipated spend |  | 10171078.44 | Anticipated spend |  | 10023336.22 | Anticipated spend |  | 0
Remaining funds |  | 567212.74 | Remaining funds |  | -398189.65 | Remaining funds |  | 2686206.0223 | Remaining funds |  | 3240483.4334 | Remaining funds |  | 13242000.5927
TRUE

## Shared Building Allocation
--this worksheet is used to allocate FRP costs for shared buildings to applicable schools.
School | GSF | FY23 Contribution | FY23 FRP funding | MRB III Adj | FY23 FRP | Contribution vs. FY23 FRP funding | FY24 Contribution | FY24 FRP funding | MRB III Adj | FY24 FRP | Contribution vs. FY24 FRP funding | FY25 Contribution | FY25 FRP funding | MRB III Adj | FY25 FRP | Contribution vs. FY25 FRP funding | FY26 Contribution | FY26 FRP funding | MRB III Adj | FY26 FRP | Contribution vs. FY26 FRP funding
Arts & Science | 1075461.7321 | 3.6638 | 1.718 | 0.55832 | 2.2763 | 1.3875 | 4.2048 | 2.6288 | -0.0094283 | 2.6193 | 1.5855 | 4.8792 | 1.5181 | 0.59153 | 2.1097 | 2.7696 | 5.3051 | -0.16904 | 0.16678 | -0.0022533 | 5.3073
School of Medicine | 280022.3999 | 0.95396 | 1.5952 | -0.55832 | 1.0369 | -0.082907 | 1.0547 | -0.026938 | 0.0094283 | -0.01751 | 1.0722 | 1.433 | 1.608 | -0.59153 | 1.0164 | 0.41656 | 1.5166 | 0.47652 | -0.16678 | 0.30974 | 1.2068
| 2748810.0535 | 4.6178 | 3.3132 |  | 3.3132 | 1.3046 | 5.2595 | 2.6018 |  | 2.6018 | 2.6577 | 6.3122 | 3.1261 |  | 3.1261 | 3.1861 | 6.8216 | 0.30748 |  | 0.30748 | 6.5141
Projects in MRBIII to be split 65% School of Medicine Basic Sciences / 35% Arts & Sciences
|  |  | FY23 |  |  |  |  | FY24 |  |  |  |  | FY25 |  |  |  |  | FY26
MRB III BIO/SCI |  |  | 1595187.5 |  |  |  |  | -26937.96 |  |  |  |  | 1690077 |  |  |  |  | 476520
A&S |  |  | 558315.625 |  |  |  |  | -9428.286 |  |  |  |  | 591526.95 |  |  |  |  | 166782
SOM |  |  | 1036871.875 |  |  |  |  | -17509.674 |  |  |  |  | 1098550.05 |  |  |  |  | 309738
|  |  | 1595187.5 |  |  |  |  | -26937.96 |  |  |  |  | 1690077 |  |  |  |  | 476520

## Summary_by School
Facility Renewal Program: Interactive Pivot Table
Row Labels | Estimated Budget | Approved_Budget
JESUP PSYCHOLOGY | 456850 | 456850
Jesup - Roof Replacement | 456850 | 456850
ONE MAGNOLIA CIRCLE | 591684 | 806417.27
One Magnolia Circle - Modify/Upgrade Electrical and Grounding | 17500 | 22000
One Magnolia Circle - Elevator Modernization | 499184 | 499184
One Magnolia Circle - Retaining Wall Repair | 75000 | 285233.27
PEABODY ADMINISTRATION | 630554 | 630554
Peabody Administration - Envelope Repairs | 630554 | 630554
SIX MAGNOLIA CIRCLE | 149000 | 148299
Six Magnolia Circle - Foundation Repairs | 149000 | 148299
WYATT CENTER | 2202627.26 | 2221968.26
Wyatt Center - Elevator #2 Modernization | 225791 | 239341
Wyatt Center - Roof Replacement | 1232681 | 1232681
Wyatt Center - VAV Replacement | 400000 | 405791
Wyatt Center - Window Replacement | 344155.26 | 344155.26
Wyatt Center Rotunda Repairs | 0 | 0
Grand Total | 4030715.26 | 4264088.53
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Project Status
Facility Renewal Program: Projects | [17 empty] | JE LOG_FY23'!A1 | JE LOG_FY24'!A1 | JE LOG_FY25'!A1 | JE LOG_FY26'!A1
| Capex / Opex | eBuilder | AiM | Oracle | School | Lookup | Building | Project | Project Status | Phase | Manager | Estimated total budget | Approved budget | Approved commitments | Projected commitments | Invoices Approved | Unallocated Reserve | FY23 FRP Transferred | FY24 FRP Transferred | FY25 FRP Transferred | FY26 FRP Transferred | FY26 FRP Estimated | FY26 FRP Total Contribution | Project status update | Check
1 | Operating | 10085 | 4591 |  | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Complete | Finalized | Sean Rewers | 17500 | 22000 | 17500 | 17500 | 17500 |  | 17500 | 0 | 0 | 0 | 0 | 0 | 03/22/2023 Project is in closeout. | 10085
2 | Capital | 10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | School of Medicine | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Complete | Finalized | Hans Mooy | 1216485.5 | 1216485.5 | 1212084.54 | 1212084.54 | 1212084.54 |  | 1216485.5 | -4400.96 | 0 | 0 | 0 | 0 | 08/22/2023 project complete | 10098
3 | Capital | 10146 | 8206 | CP_400025 | 19100 - Nursing: Business Affairs | School of Nursing | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Complete | Finalized | Sean Rewers | 318000 | 318057 | 253826.81 | 253826.81 | 253826.81 |  | 4900 | 255957 | 0 | -64230.19 | 0 | -64230.19 | 09/26/2024 Project is in library closeout. Will complete financial closeout after. | 10146
4 | Capital | 20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Fire Alarm System Replacement | Complete | Finalized | Bob Grummon | 1445389 | 1445389 | 1352423.14 | 1352423.14 | 1352423.14 |  | 722694.5 | 0 | -92965.86 | 0 | 0 | 0 | 07/29/2024 work is complete | 20179
5 | Capital | 20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Complete | Finalized | Ben Bedock | 327890 | 327890 | 280600 | 280600 | 280600 |  | 327890 | -47290 | 0 | 0 | 0 | 0 | 01/22/2024 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20336
6 | Capital | 20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Active | Warranty or Construction Closeout | Hans Mooy | 3800000 | 3800000 | 3635005.72 | 3635005.72 | 3542129.41 | 164994.28 | 69862.5 | 3660360 | 0 | 0 | 0 | 0 | 08/28/2025 Project Complete. | 20431
7 | Capital | 20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Active | Warranty or Construction Closeout | Cathy Bartlett | 2790000 | 2790000 | 2702930.48 | 2702930.48 | 2652824.48 | 0 | 81100 | 1028900 | 0 | 0 | 0 | 0 | 08/29/2025 Door hardware replacement is still not completed; once complete the project will be closed out. | 20478
8 | Capital | 20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Active | Construction | Jay Surprenant | 3600000 | 3600000 | 3287611.86 | 3287611.86 | 194523.21 |  | 26500 | 0 | 304500 | 2369000 | 0 | 2369000 | 11/25/2025 Demo is in full swing. All ceilings have been removed, AHU 1 & 2 are at 90% completed demo. New units scheduled to arrive in January. | 20489
9 | Capital | 20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Peabody | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Complete | Finalized | Ben Bedock | 456850 | 456850 | 412000 | 412000 | 412000 |  | 79415.5 | -44850 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared. | 20497
10 | Capital | 20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Window Replacement | Complete | Finalized | Ben Bedock | 344155.26 | 344155.26 | 307776.26 | 307776.26 | 307776.26 |  | 344155.26 | -36379 | 0 | 0 | 0 | 0 | 09/22/2023 Project complete. Financial closeout process to begin after confirmation that all invoices have been submitted, approved and cleared. | 20506
11 | Capital | 20560 | 4602 |  | 17000 - Law School: Office of the Dean | Law | LAW SCHOOL | Law School - Electrical Gear Replacement - FY23 FR | Deferred / On Hold | Design | Sean Rewers | 905610 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 2/13/23 This project has been placed in a deferred status while we wait for an electrical master plan to be completed. See email in documents folder for more details. | 20560
12 | Capital | 20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - VAV Replacement | Complete | Finalized | Sean Rewers | 400000 | 405791 | 362559.64 | 362559.64 | 362559.64 |  | 405791 | -43231.36 | 0 | 0 | 0 | 0 | 01/22/2024 Project is in closeout | 20562
13 | Capital | 20563 | 4624 |  | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Deferred / On Hold | Not Started | Ben Bedock | 386000 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | On hold per FRP 07/24/2024 until summer of 2026 | 20563
14 | Capital | 20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Complete | Finalized | Ben Bedock | 781870 | 781870 | 722586.68 | 722586.68 | 722586.68 |  | 781870 | -59283.32 | 0 | 0 | 0 | 0 | 11/22/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20566
15 | Capital | 20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Roof Replacement | Complete | Finalized | Ben Bedock | 1232681 | 1232681 | 1113460 | 1113460 | 1113460 |  | 1232681 | -119221 | 0 | 0 | 0 | 0 | 01/22/2024 Project is complete. Waiting on final invoice to clear to begin the closeout process. | 20573
16 | Capital | 20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | School of Medicine | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Complete | Finalized | Sean Rewers | 218202 | 218202 | 195665 | 195665 | 195665 |  | 218202 | -22537 | 0 | 0 | 0 | 0 | 01/22/2024 Project is in closeout | 20574
17 | Capital | 20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Active | Construction | Jay Surprenant | 1300000 | 1300000 | 1105354.21 | 1105354.21 | 1104104.21 |  | 223000 | 0 | 1077000 | 0 | 0 | 0 | 11/25/2025 AHU installation completed. System is currently up and running, space is conditioned and running well. Temp unit has been removed and all construction fencing is removed. waiting on commissioning. no change from last month | 20577
18 | Capital | 20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Complete | Finalized | Ben Bedock | 630554 | 630554 | 571789 | 571789 | 571789 |  | 630554 | -58765 | 0 | 0 | 0 | 0 | 10/23/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20644
19 | Operating | 20645 | 8239 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Complete | Finalized | Ben Bedock | 125875 | 125875 | 114350 | 114350 | 114350 |  | 125875 | -11525 | 0 | 0 | 0 | 0 | 02/26/2024 Punchlist items have been discussed with the contractor. Once items are completed, project is ready to closeout. | 20645
20 | Capital | 20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Active | Construction | Kylie Mignoli | 1550000 | 1545360 | 1500154.4 | 1500154.4 | 1384276.78 |  | 146500 | 0 | 1398860 | 0 | 0 | 0 | 11/25/2025 Start up of DOAS units have been pushed to December 3rd. Testing and Balancing will happen 12/8-12/10 with commissioning happening 12/12. | 20667
21 | Capital | 20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Engineering | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Active | Design | Sean Rewers | 3960000 | 231433 | 231433 | 231433 | 116143 |  | 206500 | 24933 | 0 | 0 | 0 | 0 | 11/21/2025 We are awaiting definitive plans from the CUI project to determine where our chilled water connection will be. If hot water goes past the building as part of CUI we will rework the design to include hot water connection. | 20668
22 | Capital | 20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Complete | Finalized | Sean Rewers | 680000 | 678513 | 586776.36 | 586776.36 | 586776.36 |  | 29250 | 649263 | 0 | -91736.64 | 0 | -91736.64 | 11/25/2024 Project in FX | 20698
23 | Operating | 20700 | 851 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Complete | Finalized | Sean Rewers | 80000 | 85577 | 85576.77 | 85576.77 | 85576.77 |  | 79623 | 5954 | 0 | 0 | 0 | 0 | 11/27/2023 Project is in closeout | 20700
24 | Capital | 20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Complete | Finalized | Sean Rewers | 500000 | 499093 | 447535.86 | 447535.86 | 447535.86 | 51582.14 | 499093 | 0 | 0 | -51557.14 | 0 | -51557.14 | 06/25/2025 Final walkthrough scheduled for July 3rd with VUMO, envision and Sylvan. | 20701
25 | Capital | 20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Complete | Finalized | Ben Bedock | 225791 | 239341 | 209419 | 209419 | 209419 |  | 239341 | -29922 | 0 | 0 | 0 | 0 | 12/18/2023 Project complete. Waiting on final invoice to clear to begin the financial closeout process. | 20702
26 | Capital | 20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Complete | Finalized | Erin Fry | 715000 | 715000 | 656784.6 | 656784.6 | 656576.59 |  | 96166 | 0 | 0 | 0 | 0 | 0 | 02/23/2024 Construction complete. Library Closeout process complete. The Financial closeout process has been started. | 20718
27 | Capital | 20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | School of Medicine | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Active | Construction | Jay Surprenant | 1610000 | 1700000 | 1538240.72 | 1538240.72 | 1146822.02 |  | 160500 | 0 | 1539500 | 0 | 0 | 0 | 11/25/2025 Updated drawings received. Working through the last 5 phases now. Two phases (7 & 8) will be delayed until we can do the office renovation in concurrence with the HVAC controls in order to minimize disruption to the lab space. Current target to completion is end of January, pending budget approval for office buildout associated with Deans Space Reallocation project. | 20723
28 | Capital | 20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Active | Financial Closeout | Hans Mooy | 1987500 | 1987500 | 1873174.63 | 1873174.63 | 1839258.28 | 114325.37 | 23400 | 1964100 | 0 | -148241.72 | 0 | -148241.72 | 05/22/2025 Project complete. | 20724
29 | Operating | 20735 | 8226 |  | 20000 - Owen: Office of the Dean | Owen | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Complete | Finalized | Ben Bedock | 300000 | 300000 | 276500 | 276500 | 276500 |  | 300000 | -23500 | 0 | 0 | 0 | 0 | 04/23/2024 Project is complete. | 20735
30 | Capital | 20767 | 8673 | CP_400242 | 21000 - Peabody College: Office of the Dean | Peabody | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Active | Warranty or Construction Closeout | Jay Surprenant | 149000 | 148299 | 125699 | 125699 | 125699 | 22600 | 0 | 148299 | 0 | 0 | 0 | 0 | 08/28/2025 Moving through LC process. no change from last month. | 20767
31 | Operating | 20771 | 8674 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Complete | Finalized | Sean Rewers | 25000 | 24997 | 17972 | 17972 | 17972 |  | 24997 | -7025 | 0 | 0 | 0 | 0 | 07/24/2023 Project is complete. I will begin closeout after taking some final photos of the space. | 20771
32 | Capital | 20772 | 8675 | CP_400235 | 20100 - Owen: Business Affairs | Owen | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Complete | Finalized | Ben Bedock | 3200000 | 3200000 | 2977388.14 | 2977388.14 | 2977388.14 |  | 0 | 1600000 | 1600000 | -222611.86 | 0 | -222611.86 | 04/23/2025 Awaiting final invoice to clear to begin the close out process | 20772
33 | Capital | 20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Complete | Finalized | Ben Bedock | 400000 | 483440 | 450775 | 450775 | 450775 |  | 483440 | -32665 | 0 | 0 | 0 | 0 | 12/18/2023 Construction complete. Waiting on final invoices to clear to begin the closeout process. | 20792
34 | Capital | 20811 | 8729 | CP_400224 | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Retaining Wall Repair | Complete | Finalized | Ben Bedock | 75000 | 285233.27 | 255013.19 | 255013.19 | 123523.71 | 30220.08 | 0 | 285233.27 | 0 | -161709.56 | 0 | -161709.56 | 04/23/2025 Project is complete. Waiting on final invoices to clear to begin the closeout process. | 20811
35 | Capital | 20812 | 8923 | CP_400282 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE GARAGE | 1025 16th Avenue - Patio Repairs | Active | Construction | Sean Rewers | 485000 | 486135 | 405008.05 | 405008.05 | 377024.69 |  |  |  | 486135 |  | 0 | 0 | 11/21/2025 Patio pours are complete, stairs have been poured, concrete to the sidewalk has been poured. Masonry is mostly complete against the building; we still need to complete the exhaust vent dormer and pour topping slab. THP has reviewed the site and made suggestions to ensure no water is entering the building and asked for water tests. Work has started to seal cracks from below. Lighting is pushed back to the new year. | 20812
36 | Operating | 20831 | 8230 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Complete | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 01/30/2024 Project is in closeout. Study was completed and findings were shared with Provost and A&S. Due to the large scale renovations needed to the building this project will require further planning and cannot be priced our accurately. A&S will present the findings to their dean for further guidance on how to tackle the buildings issues. | 20831
37 | Operating | 20832 | 8220 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - HVAC Replacement | Complete | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 01/22/2024 Project study and estimated pricing is complete. Project in closeout. | 20832
38 | Operating | 20833 | 8215 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement (Design Services) | Complete | Finalized | Sean Rewers | 24000 | 24000 | 24000 | 24000 | 24000 |  | 0 | 24000 | 0 | 0 | 0 | 0 | 04/24/2024 Project is in closeout | 20833
39 | Capital | 20857 | 8427 | CP_400227 | 21000 - Peabody College: Office of the Dean | Peabody | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Elevator Modernization | Active | Construction Closeout | Ben Bedock | 499184 | 499184 | 483144.67 | 483144.67 | 481346.67 | 16039.33 | 0 | 499184 | 0 | 0 | 0 | 0 | 08/26/2025 Complete. Working through punchlist items. Waiting on invoices to clear and one year review. | 20857
40 | Capital | 20884 | 8807 | CP_400251 | 17000 - Law: Office of the Dean | Law | LAW SCHOOL | Law School - Exterior Window Painting | Complete | Finalized | Ben Bedock | 675650 | 675650 | 480318 | 480318 | 480318 | 195332 | 0 | 675650 | 0 | -195332 | 0 | -195332 | 08/23/2024 VUMO is managing this project. CPC is helping with the PO/financial process. | 20884
41 | Operating | 20885 | 8676 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Active | Financial Closeout | Sean Rewers | 130000 | 143053.4 | 123743.89 | 123743.89 | 123743.89 | 19309.51 | 0 | 113053.4 | 30000 | -19309.51 | 0 | -19309.51 | 06/25/2025 Walkthrough has been completed and all punch items are finished, except sequencing. JCI was contacted to do the work but they are forwarding it to the JCI staff who work at the university. This is the last bit of programming and then project can be closed out. | 20885
42 | Operating | 20911 | 8819 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - Elevator Upgrades | Complete | Finalized | Ben Bedock | 61045 | 61045 | 54613 | 54613 | 54613 |  | 0 | 61045 | 0 | -6432 | 0 | -6432 | 03/25/2025 Construction complete and inspection passed. Waiting on invoices to clear to begin the closeout process. | 20911
43 | Operating | 20912 | 8822 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BENSON OLD CENTRAL | Benson Hall - Elevator Upgrades | Active | Financial Closeout | Ben Bedock | 59798 | 59798 | 53366 | 53366 | 53366 | 6432 | 0 | 59798 | 0 | 0 | 0 | 0 | 08/26/2025 Construction complete and inspection passed. Waiting on invoices to clear to begin the closeout process. | 20912
44 | Operating | 20913 | 8818 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Elevator Upgrades | Active | Financial Closeout | Ben Bedock | 96612 | 96612 | 86900 | 86900 | 86900 | 9712 | 0 | 96612 | 0 | 0 | 0 | 0 | 05/22/2025 Construction complete and inspection passed. Invoices are cleared. Financial closeout process has started. | 20913
45 | Capital | 20922 | 8720 | CP_400263 | 12000 - Arts and Science: Office of the Dean | Arts & Science | VAUGHN HOME | Vaughn Home - Exterior Improvements | Active | Warranty or Construction Closeout | Jay Surprenant | 170000 | 197150 | 170000 | 170000 | 170000 | 27150 | 0 | 197150 | 0 | 0 | 0 | 0 | 08/28/2025 Moved to library closeout. waiting on closeout documents from contractor. No change from last month. | 20922
46 | Operating | 20924 | 8737 |  | 19000 - Nursing: Office of the Dean | School of Nursing | FRIST HALL | Frist Hall - Stairwell Roof Replacement | Complete | Finalized | Ben Bedock | 30570 | 30570 | 24500 | 24500 | 24500 |  | 0 | 30570 | -6070 | 0 | 0 | 0 | 11/26/2024 Construction is complete. Waiting on the final invoice to begin the closeout process. | 20924
47 | Capital | 20925 | 8260 | CP_400326 | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | Active | Construction | Jay Surprenant | 2125000 | 2125000 | 1860577 | 1860577 | 287445 |  | 0 | 0 | 409000 | 1716000 | 0 | 1716000 | 11/25/2025 Temporary units are being tied in now. Switch over to temp units scheduled for December before demo can begin. | 20925
48 | Operating | 20936 | 8814 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - Lighting Retrofit for 103 and 126 | Active | Warranty or Construction Closeout | Jay Surprenant | 405000 | 404655.91 | 357255.91 | 357255.91 | 357255.91 | 47400 | 0 | 404655.91 | 0 | 0 | 0 | 0 | 08/28/2025 Project completed. Moving to Library Closeout. No change from last month. | 20936
49 | Capital | 20940 | 8412 | CP_400291 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Security System Replacement | Active | Financial Closeout | Sean Rewers | 310000 | 309548.64 | 298567.26 | 298567.26 | 298567.26 | 10981.38 | 0 | 0 | 309548.64 | 0 | 0 | 0 | 06/24/2025 Project is in closeout | 20940
50 | Operating | 20945 | 8905 |  | 10000 - Chancellor | Other | SEIGENTHALER CENTER | Seigenthaler Building - HVAC Improvements | Complete | Finalized | Sean Rewers | 99000 | 99000 | 82897 | 82897 | 70200 | 16103 | 0 | 99000 | 0 | -28800 | 0 | -28800 | 11/25/2024 We are awaiting TAB and other reports from Nashville Machine, then we will put into FX. | 20945
51 | Capital | 20958 | 1642 | CP_400256 | 12000 - Arts and Science: Office of the Dean | Arts & Science | FURMAN HALL | Furman Hall - Elevator Modernization | Active | Construction Closeout | Ben Bedock | 290000 | 261629 | 239133 | 239133 | 137776.91 |  | 0 | 18175 | 243454 | 0 | 0 | 0 | 10/28/2025 Electrical and Mechanical requirements are the last of the items to be completed. Once items are finished, Lerch Bates to do a final inspection before project can be written as complete. | 20958
52 | Capital | 20962 | 8754 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | VAUGHN HOME | Vaughn Home - Roof Replacement | Active | Design | Ben Bedock | 1750000 | 1800 | 1800 | 1800 | 1800 |  | 0 | 0 | 1800 | 0 | TBD | TBD | 11/26/2025 Summer 2026 project. Internal parties are determining the best solution for the project and the future of the building. | 20962
53 | Capital | 20979 | 9 | CP_400330 | 15000 - Engineering: Office of the Dean | Engineering | 1025 16TH AVE S | 1025 16th Avenue - Roof Replacement | Active | Construction | Ben Bedock | 270000 | 581188 | 527438 | 527438 | 365000 |  | 0 | 0 | 529750 | 51438 | 51438 | 102876 | 11/26/2025 Construction is scheduled to start on 12/15/2025. | 20979
54 | Capital | 20982 | 8442 | CP_400270 | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Elevator 1 Modernization | Active | Construction Closeout | Ben Bedock | 272000 | 272000 | 249821 | 249821 | 246321 | 22179 | 0 | 18175 | 253825 | 0 | 0 | 0 | 08/26/2025 Complete. Working through punchlist items. Waiting on invoices to clear and one year review. | 20982
55 | Operating | 20984 | 8712 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | WILSON HALL | Wilson Hall - 1st Floor Urinal Replacement | Active | Financial Closeout | Hans Mooy | 167000 | 167000 | 143484.6 | 143484.6 | 136652 | 23515.4 | 0 | 0 | 167000 | 0 | 0 | 0 | 05/22/2025 Project complete... | 20984
56 | Capital | 21004 | 1010 | CP_400332 | 12100 - Arts and Science: Business Affairs | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | Active | Construction | Jay Surprenant | 940000 | 992453 | 811113 | 811113 | 37400 |  | 0 | 0 | 992453 | 0 | 0 | 0 | 11/25/2025 Pushing this work to FY 25/26, summer '26. Equipment is on order. | 21004
57 | Capital | 21005 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 4, 5, and 7 (Phase 2) | Deferred / On Hold | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 09/24/2024 This is FY 26 project. No updates to provide yet. Project not started. | 21005
58 | Capital | 21006 |  |  | 15000 - Engineering: Office of the Dean | Engineering | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 3 and 6 (Phase 3) | Deferred / On Hold | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | TBD | TBD | 09/24/2024 Project not started. this is an FY28 project. | 21006
59 | Capital | 21007 |  |  | 15000 - Engineering: Office of the Dean | Engineering | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 8 and 9 (Phase 4) | Deferred / On Hold | Programming or Planning | Jay Surprenant | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 09/24/2024 Project not started. This is an FY29 project. | 21007
60 | Capital | 21010 |  | CP_400312 | 15000 - Engineering: Office of the Dean | Engineering | FEATHERINGILL-JACOBS HALL | Featheringill-Jacobs Hall - Hot Water Tank Replacement | Active | Financial Closeout | Sean Rewers | 125000 | 126024 | 112824.84 | 112824.84 | 112824.84 | 13583.3 | 0 | 0 | 126024 | -13199.16 | 0 | -13199.16 | 05/23/2025 New disconnect is installed, with conduit and wire ran back to the elec. room. UO scheduled for June 3 which will likely be last piece of the project. Old HX demo is complete, and the new water heater was placed into the Basement 5/21. Piping work is ongoing. | 21010
61 | Operating | 21035 |  |  | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Roof Ladders | Active | Financial Closeout | Ben Bedock | 50000 | 36108.16 | 32589.24 | 32589.24 | 32589.24 | 3518.92 |  |  | 36108.16 | 0 | 0 | 0 | 08/26/2025 Project complete. | 21035
62 | Capital | 21051 | 8784 | CP_400344 | 18200 - Basic Sciences: Office of the Dean | School of Medicine | MRB III BIO/SCI | MRBIII - 5th Floor Controls | Active | Programming or Planning | Ben Bedock | 0 | 27500 | 0 | 0 | 0 |  | 0 | 0 | 0 | 27500 | 1600000 | 1627500 | 11/25/2025 BAC approved, CA is in progress. | 21051
63 | Capital | 21066 |  | CP_400314 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC MOLEC BIOLOGY | SC2 - MEP Feasibility Study | Active | Programming or Planning | Sean Rewers | 29160 | 29160 | 29160 | 29160 | 24786 |  | 0 | 0 | 29160 | 0 | 0 | 0 | 11/20/2025 We have reviewed AEIs draft study with A&S and assets. We are awaiting a few other conversations on the future of these buildings before giving AEI a direction for a final report. | 21066
64 | Capital | 21067 |  | CP_400311 | 19000 - Nursing: Office of the Dean | School of Nursing | GODCHAUX HALL | Godchaux Hall - Phase 2 HVAC Upgrades and Roof Replacement | Active | Bidding | Sean Rewers | 2500000 | 46600 | 46600 | 46600 | 22810 |  | 0 | 0 | 46600 | 0 | 2100000 | 2100000 | 11/21/2025 We are awaiting all comments from VU engineering before final drawings are stamped. We have spoken to building managers and they understand the scope and timeline. Longest lead time is 12 weeks so getting the bid out in December is acceptable to meet summer 2026 schedule. | 21067
65 | Operating | 21068 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | BUTTRICK HALL | Buttrick Hall - Insulate First Floor Slab | Active | Construction Closeout | Jay Surprenant | 0 | 34837.4 | 24737.4 | 24737.4 | 24737.4 | 10100 | 0 | 0 | 34837.4 | 0 | 0 | 0 | 05/28/2025 Scheduled for early June completion. | 21068
66 | Operating | 21070 | 8733 |  | 15000 - Engineering: Office of the Dean | Engineering | OLIN HALL | Olin Hall - Exterior Facade Cleaning | Active | Financial Closeout | Ben Bedock | 848722 | 392042.1 | 331331 | 331331 | 308101 | 60771.1 | 0 | 0 | 392042.1 | 0 | 0 | 0 | 08/26/2025 Construction Complete. Awaiting final invoice to begin closeout process | 21070
67 | Capital | 21071 |  | CP_400313 | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC MATH | SC1 - MEP Feasibility Study | Active | Programming or Planning | Sean Rewers | 19440 | 19440 | 19440 | 19440 | 16524 |  | 0 | 0 | 19440 | 0 | 0 | 0 | 11/20/2025 We have reviewed AEIs draft study with A&S and assets. We are awaiting a few other conversations on the future of these buildings before giving AEI a direction for a final report. | 21071
68 | Operating | 21072 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | CALHOUN HALL | Calhoun Hall - MEP Feasibility Study | Deferred / On Hold | Award | Sean Rewers | 10000 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | Project is deferred to late 2026. We do not currently have funding in A&S for this project. | 21072
69 | Operating | 21073 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | FURMAN HALL | Furman Hall - MEP Feasibility Study | Deferred / On Hold | Award | Sean Rewers | 10000 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | Project is being deferred to late 2026. We do not currently have A&S budget to cover this project. | 21073
70 | Operating | 21074 |  |  | 17000 - Law: Office of the Dean | Law | LAW SCHOOL | Law School - MEP Feasibility Study | Deferred / On Hold | Award | Sean Rewers | 10000 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | Project is being deferred to FY27, as project start will not be until FY28 | 21074
71 | Operating | 21094 |  |  | 17000 - Law: Office of the Dean | Law | GODCHAUX HALL | Godchaux Hall - Replace Fire Pump | Active | Financial Closeout | Sean Rewers | 87500 | 87500 | 48640 | 48640 | 48640 |  | 0 | 0 | 87500 | 0 | 0 | 0 | 09/29/2025 Project has been completed, awaiting warranty and manuals. Will confirm with BSC that tests were completed and passed. | 21094
72 | Operating | 21108 |  |  | 19100 - Nursing: Business Affairs | School of Nursing | 1025 16TH AVE S | 1025 16th Avenue - Electrical and HVAC Study | Complete | Finalized | Sean Rewers | 5000 | 5000 | 5000 | 5000 | 5000 |  | 0 | 0 | 5000 | 0 | 0 | 0 | 04/29/2025 Project in closeout | 21108
73 | Operating | 21113 |  |  | 15000 - Engineering: Office of the Dean | Engineering | MRB III BIO/SCI | MRBIII - Lecture Hall V1220 Lighting Upgrade | Active | Construction | Jay Surprenant | 85000 | 82125 | 61963.84 | 61963.84 | 0 |  | 0 | 0 | 82125 | 0 | 0 | 0 | 11/25/2025 Schedule currently set for winter break: 12/22 - 1/4/26. | 21113
74 | Operating | 21114 |  |  | 18200 - Basic Sciences: Office of the Dean | School of Medicine | MRB III BIO/SCI | MRBIII - Chemical Discharge Tank Replacement | Active | Construction | Jay Surprenant | 70000 | 68452 | 53802 | 53802 | 0 |  | 0 | 0 | 68452 | 0 | 0 | 0 | 11/25/2025 All equipment is in hand with the contractor. Working on scheduling this as off-hour work to avoid shutdowns of labs. | 21114
75 | Capital | 21127 |  | CP_400334 | 18200 - Basic Sciences: Office of the Dean | School of Medicine | MRB III BIO/SCI | MRBIII - Cooling Tower Overhaul | Active | Construction | Jay Surprenant | 450000 | 449020 | 356319 | 356319 | 0 |  | 0 | 0 | 0 | 449020 | 0 | 449020 | 11/24/2025 1st of four towers is completed. contractor is currently working on the second tower. Targeting 01/01/26 completion. | 21127
76 | Operating | 21155 | 904 |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC MOLEC BIOLOGY | SC2 Restroom Upgrades | Active | Programming or Planning | Daniel Capparella | 750000 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 750000 | 750000 | 11/24/2025 Held site visit 11/10/25. Drafting scope. | 21155
77 | Capital | 21156 |  | CP_400337 | 15000 - Engineering: Office of the Dean | Engineering | OLIN HALL | Olin Hall 2nd Floor Chiller | Active | Construction | Nickolaus Corniea | 500000 | 386000 | 352551.19 | 352551.19 | 10800 |  |  |  |  | 386000 | 340000 | 726000 | 12/05/2025 11/05/2025 Orion Construction will manage this work alongside their efforts for Olin Hall lab renovations. This work is estimated to be completed spring 2026. | 21156
78 | Operating | 21157 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | COHEN MEMORIAL | Cohen Memorial - Water Intrusion Repair | Active | Design | Jay Surprenant | 250000 | 19000 | 12700 | 12700 | 9800 |  |  |  |  | 0 | 25000 | 25000 | 11/24/2025 engineers report received, sent to stakeholders for review. waiting on responses back. | 21157
79 | TBD | 21165 |  |  | 21000 - Peabody College: Office of the Dean | Peabody | WYATT CENTER | Wyatt Center Rotunda Repairs | Active | Programming or Planning | Ben Bedock | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | TBD | TBD | 11/26/2025 Meeting with the Zone manager to determine scope of work and budget. | 21165
80 | Capital | 21173 |  | CP_400343 | 22000 - College of Connected Computing: Office of the Dean | College of Connected Computing | 17TH & HORTON | 17th & Horton Elevators Modernization | Active | Programming or Planning | Ben Bedock | 575000 | 25550 | 0 | 25550 | 0 |  |  |  |  | 25550 | 25550 | 51100 | 11/26/2025 Working through the PO for the elevator consultant. | 21173
81 | Operating | 21174 |  |  | 12100 - Arts and Science: Business Affairs | Arts & Science | BUTTRICK HALL | Buttrick Hall - Restore / Replace Exterior Wood Doors and Closures | Active | Not Started | Erin Fry | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | TBD | TBD | 11/24/2025 Meeting with stakeholders to determine scope of work and budget. | 21174
82 | Capital | 21175 |  |  | 12100 - Arts and Science: Business Affairs | Arts & Science | LAW SCHOOL | Law School Partial Roof Replacement | Active | Programming or Planning | Ben Bedock | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | TBD | TBD | 11/26/2025 Met with VUMO engineering to determine the needs for mechanical equipment on the roof that are in the way for replacement. It is determined that building a penthouse around the equipment is the best option. | 21175
83 | Operating | 21176 |  |  | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School Walkway Replacement | Active | Design | James Moore | 160000 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 160000 | 160000 | 11/24/2025 Scope approved by Law School. Handing off to James. | 21176
84 | Capital | 21177 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC MOLEC BIOLOGY | SC2 Molecular Biology HVAC Replacement | Active | Not Started | Daniel Capparella | 2215000 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | TBD | TBD | 11/24/2025 Held site visit 11/10/25. Drafting scope. | 21177
85 | Operating | 21178 |  |  | 17100 - Law: Business Affairs | Law | LAW SCHOOL | Law School - Air Compressor Replacement #6 | Active | Construction | Kylie Mignoli | 30000 | 75000 | 24132 | 24132 | 2500 |  |  |  |  | 75000 | 75000 | 150000 | 11/20/2025 Narrative was created for the project. Nashville Machine bid and bid was found appropriate. Po is in process for Nashville Machine for a winter break install. UO already submitted and discussions with zone and building manager completed for means and methods. | 21178
86 | Capital | 21189 |  |  | 13000 - Blair: Office of the Dean | Blair | BLAIR SCHOOL OF MUSIC | Blair School Legacy VAV Replacement and Duct Encapsulation | Active | Programming or Planning | Ben Bedock | 800000 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 800000 | 800000 | 11/26/2025 Planning stage gate letter sent to appropriate parties for signature. Once returned, project will move to design. | 21189
87 | Capital | 21198 |  |  | 12000 - Arts and Science: Office of the Dean | Arts & Science | SC CHEMISTRY | SC7 - AHUs Replacement | Active | Programming or Planning | Sean Rewers | 1300000 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | TBD | TBD | 11/26/2025 Working with appropriate parties to determine the scope of work and next steps. | 21198
[12 empty] | 55542033.76 | 40584416.64 | 36917436.9 | 36942986.9 | 29335787.7 | 865848.81 | 8797286.26 | 11427472.94 | 10171078.44 | 4096348.22 | 5926988 | 10023336.22
[18 empty] | TRUE | TRUE | TRUE | TRUE
[18 empty] | TRUE | TRUE | TRUE | TRUE
Projects to be discussed
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes roof repairs in scope.
Note on M10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S swing space and FRP scope.
Note on V11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project will be joint funded, FPR / Divinity + Dean of Students. Reply: The split should be 75% Divinity (FRP) and 25% Student Affairs.
Note on M29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Includes both A&S third floor renovation FRP (VAV boxes) scope.
Note on I39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.
Note on I41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Feasibility study to occur FY24 as opex cost. Unsure timing of eventual construction.

## Summary_by FY
FY 2023 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred |  | FRP Funding | Remaining
| 1 | 10085 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Finalized | Sean Rewers | 9364499 | 17500 |  | 17500
| 2 | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Finalized | Hans Mooy |  | 1216485.5 |  | 1216485.5
| 3 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Finalized | Sean Rewers |  | 4900 |  | 4900
| 4 | 20179 | LAW SCHOOL | Law School - Fire Alarm System Replacement | Finalized | Bob Grummon |  | 722694.5 |  | 722694.5
| 5 | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Finalized | Ben Bedock |  | 327890 |  | 327890
| 6 | 20431 | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Warranty or Construction Closeout | Hans Mooy |  | 69862.5 |  | 69862.5
| 7 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Warranty or Construction Closeout | Cathy Bartlett |  | 81100 |  | 81100
| 8 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Construction | Jay Surprenant |  | 26500 |  | 26500
| 9 | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Finalized | Ben Bedock |  | 79415.5 |  | 79415.5
| 10 | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Finalized | Ben Bedock |  | 344155.26 |  | 344155.26
| 11 | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Finalized | Sean Rewers |  | 405791 |  | 405791
| 12 | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Finalized | Ben Bedock |  | 781870 |  | 781870
| 13 | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Finalized | Ben Bedock |  | 1232681 |  | 1232681
| 14 | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Finalized | Sean Rewers |  | 218202 |  | 218202
| 15 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Construction | Jay Surprenant |  | 223000 |  | 223000
| 16 | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Finalized | Ben Bedock |  | 630554 |  | 630554
| 17 | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Finalized | Ben Bedock |  | 125875 |  | 125875
| 18 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Construction | Kylie Mignoli |  | 146500 |  | 146500
| 19 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  | 206500 |  | 206500
| 20 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Finalized | Sean Rewers |  | 29250 |  | 29250
| 21 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Finalized | Sean Rewers |  | 79623 |  | 79623
| 22 | 20701 | SC SCIENCE & ENGINEERING | SC-5 - Chemical Discharge Replacement | Finalized | Sean Rewers |  | 499093 |  | 499093
| 23 | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Finalized | Ben Bedock |  | 239341 |  | 239341
| 24 | 20718 | BUTTRICK HALL | Buttrick Hall - 3rd Floor Inequality Renovations | Finalized | Erin Fry |  | 96166 |  | 96166
| 25 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Construction | Jay Surprenant |  | 160500 |  | 160500
| 26 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Financial Closeout | Hans Mooy |  | 23400 |  | 23400
| 27 | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Finalized | Ben Bedock |  | 300000 |  | 300000
| 28 | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers |  | 24997 |  | 24997
| 29 | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Finalized | Ben Bedock |  | 483440 |  | 483440
[8 empty] | 8797286.26 | 0 | 8797286.26 | 567212.74
TRUE
FY 2024 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred |  | FRP Funding | Remaining
| 1 | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Finalized | Sean Rewers | 11029283.29 | 255957 |  | 255957
| 2 | 20431 | DIVINITY | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Warranty or Construction Closeout | Hans Mooy |  | 3660360 |  | 3660360
| 3 | 20478 | BRYAN BLDG | Bryan Building - Swing Space Renovation - A&S Planning | Warranty or Construction Closeout | Cathy Bartlett |  | 1028900 |  | 1028900
| 4 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  | 24933 |  | 24933
| 5 | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Finalized | Sean Rewers |  | 649263 |  | 649263
| 6 | 20700 | SC CHEMISTRY | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Finalized | Sean Rewers |  | 5954 |  | 5954
| 7 | 20724 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Steam Line - FY 23 | Financial Closeout | Hans Mooy |  | 1964100 |  | 1964100
| 8 | 20767 | SIX MAGNOLIA CIRCLE | Six Magnolia Circle - Foundation Repairs | Warranty or Construction Closeout | Jay Surprenant |  | 148299 |  | 148299
| 9 | 20772 | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Finalized | Ben Bedock |  | 1600000 |  | 1600000
| 10 | 20811 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Retaining Wall Repair | Finalized | Ben Bedock |  | 285233.27 |  | 285233.27
| 11 | 20831 | SC PHYSICS & ASTRONOMY | SC6 - HVAC Upgrades - Feasibility Study | Finalized | Sean Rewers |  | 24000 |  | 24000
| 12 | 20832 | WILSON HALL | Wilson Hall - HVAC Replacement | Finalized | Sean Rewers |  | 24000 |  | 24000
| 13 | 20833 | SC SCIENCE & ENGINEERING | SC5 - HVAC Replacement (Design Services) | Finalized | Sean Rewers |  | 24000 |  | 24000
| 14 | 20857 | ONE MAGNOLIA CIRCLE | One Magnolia Circle - Elevator Modernization | Construction Closeout | Ben Bedock |  | 499184 |  | 499184
| 15 | 20884 | LAW SCHOOL | Law School - Exterior Window Painting | Finalized | Ben Bedock |  | 675650 |  | 675650
| 16 | 20885 | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Financial Closeout | Sean Rewers |  | 113053.4 |  | 113053.4
| 17 | 20911 | BUTTRICK HALL | Buttrick Hall - Elevator Upgrades | Finalized | Ben Bedock |  | 61045 |  | 61045
| 18 | 20912 | BENSON OLD CENTRAL | Benson Hall - Elevator Upgrades | Financial Closeout | Ben Bedock |  | 59798 |  | 59798
| 19 | 20913 | WILSON HALL | Wilson Hall - Elevator Upgrades | Financial Closeout | Ben Bedock |  | 96612 |  | 96612
| 20 | 20922 | VAUGHN HOME | Vaughn Home - Exterior Improvements | Warranty or Construction Closeout | Jay Surprenant |  | 197150 |  | 197150
| 21 | 20924 | FRIST HALL | Frist Hall - Stairwell Roof Replacement | Finalized | Ben Bedock |  | 30570 |  | 30570
| 22 | 20936 | WILSON HALL | Wilson Hall - Lighting Retrofit for 103 and 126 | Warranty or Construction Closeout | Jay Surprenant |  | 404655.91 |  | 404655.91
| 23 | 20945 | SEIGENTHALER CENTER | Seigenthaler Building - HVAC Improvements | Finalized | Sean Rewers |  | 99000 |  | 99000
| 24 | 20958 | FURMAN HALL | Furman Hall - Elevator Modernization | Construction Closeout | Ben Bedock |  | 18175 |  | 18175
| 25 | 20982 | LAW SCHOOL | Law School - Elevator 1 Modernization | Construction Closeout | Ben Bedock |  | 18175 |  | 18175
|  | 10098 | MRB III BIO/SCI | MRB III - 4th Floor - Replace Controls (Phase 2) | Finalized | Hans Mooy |  | -4400.96 |  | -4400.96
|  | 20336 | BLAIR SCHOOL OF MUSIC | Blair School of Music - Elevator #3 Modernization | Finalized | Ben Bedock |  | -47290 |  | -47290
|  | 20497 | JESUP PSYCHOLOGY | Jesup - Roof Replacement | Finalized | Ben Bedock |  | -44850 |  | -44850
|  | 20506 | WYATT CENTER | Wyatt Center - Window Replacement | Finalized | Ben Bedock |  | -36379 |  | -36379
|  | 20562 | WYATT CENTER | Wyatt Center - VAV Replacement | Finalized | Sean Rewers |  | -43231.36 |  | -43231.36
|  | 20566 | SC CHEMISTRY | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Finalized | Ben Bedock |  | -59283.32 |  | -59283.32
|  | 20573 | WYATT CENTER | Wyatt Center - Roof Replacement | Finalized | Ben Bedock |  | -119221 |  | -119221
|  | 20574 | MRB III BIO/SCI | MRB III - Steam Coil Replacement | Finalized | Sean Rewers |  | -22537 |  | -22537
|  | 20644 | PEABODY ADMINISTRATION | Peabody Administration - Envelope Repairs | Finalized | Ben Bedock |  | -58765 |  | -58765
|  | 20645 | BENSON OLD CENTRAL | Benson Old Central - Replace Soffit and Doors | Finalized | Ben Bedock |  | -11525 |  | -11525 | prior year
|  | 20702 | WYATT CENTER | Wyatt Center - Elevator #2 Modernization | Finalized | Ben Bedock |  | -29922 |  | -29922 | carryforward
|  | 20771 | SC CHEMISTRY | SC4 - Interstitial Space HVAC Modifications | Finalized | Sean Rewers |  | -7025 |  | -7025
|  | 20792 | LAW SCHOOL | Law School - Sections 1, 2, & 3 Roof Replacement | Finalized | Ben Bedock |  | -32665 |  | -32665 | 567212.74
|  | 20735 | OWEN GRAD MGMT | Owen - Roof Replacement (Third Level) | Finalized | Ben Bedock |  | -23500 |  | -23500
[8 empty] | 11427472.94 | 0 | 11427472.94 | 169023.09
TRUE
FY 2025 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred |  | FRP Funding | Remaining
| 1 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Construction | Jay Surprenant | 12857284.4623 | 304500 |  | 304500
| 2 | 20577 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Construction | Jay Surprenant |  | 1077000 |  | 1077000
| 3 | 20667 | 1025 16TH AVE S | 1025 16th Avenue - Mechanical and Electrical Upgrades | Construction | Kylie Mignoli |  | 1398860 |  | 1398860
| 4 | 20723 | MRB III BIO/SCI | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Construction | Jay Surprenant |  | 1539500 |  | 1539500
| 5 | 20772 | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Finalized | Ben Bedock |  | 1600000 |  | 1600000
| 6 | 20812 | 1025 16TH AVE GARAGE | 1025 16th Avenue - Patio Repairs | Construction | Sean Rewers |  | 486135 |  | 486135
| 7 | 20885 | BIOMOLECULAR NMR | NMR - Replace Air Compressors | Financial Closeout | Sean Rewers |  | 30000 |  | 30000
| 8 | 20925 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | Construction | Jay Surprenant |  | 409000 |  | 409000
| 9 | 20940 | 1025 16TH AVE S | 1025 16th Avenue - Security System Replacement | Financial Closeout | Sean Rewers |  | 309548.64 |  | 309548.64
| 10 | 20958 | FURMAN HALL | Furman Hall - Elevator Modernization | Construction Closeout | Ben Bedock |  | 243454 |  | 243454
| 11 | 20962 | VAUGHN HOME | Vaughn Home - Roof Replacement | Design | Ben Bedock |  | 1800 |  | 1800
| 12 | 20982 | LAW SCHOOL | Law School - Elevator 1 Modernization | Construction Closeout | Ben Bedock |  | 253825 |  | 253825
| 13 | 20984 | WILSON HALL | Wilson Hall - 1st Floor Urinal Replacement | Financial Closeout | Hans Mooy |  | 167000 |  | 167000
| 14 | 21004 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | Construction | Jay Surprenant |  | 992453 |  | 992453
| 15 | 21010 | FEATHERINGILL-JACOBS HALL | Featheringill-Jacobs Hall - Hot Water Tank Replacement | Financial Closeout | Sean Rewers |  | 126024 |  | 126024
| 16 | 21066 | SC MOLEC BIOLOGY | SC2 - MEP Feasibility Study | Programming or Planning | Sean Rewers |  | 29160 |  | 29160
| 17 | 21067 | GODCHAUX HALL | Godchaux Hall - Phase 2 HVAC Upgrades and Roof Replacement | Bidding | Sean Rewers |  | 46600 |  | 46600
| 18 | 21068 | BUTTRICK HALL | Buttrick Hall - Insulate First Floor Slab | Construction Closeout | Jay Surprenant |  | 34837.4 |  | 34837.4
| 19 | 21070 | OLIN HALL | Olin Hall - Exterior Facade Cleaning | Financial Closeout | Ben Bedock |  | 392042.1 |  | 392042.1
| 20 | 21071 | SC MATH | SC1 - MEP Feasibility Study | Programming or Planning | Sean Rewers |  | 19440 |  | 19440
| 21 | 21094 | GODCHAUX HALL | Godchaux Hall - Replace Fire Pump | Financial Closeout | Sean Rewers |  | 87500 |  | 87500
| 22 | 21108 | 1025 16TH AVE S | 1025 16th Avenue - Electrical and HVAC Study | Finalized | Sean Rewers |  | 5000 |  | 5000
| 23 | 21113 | MRB III BIO/SCI | MRBIII - Lecture Hall V1220 Lighting Upgrade | Construction | Jay Surprenant |  | 82125 |  | 82125
| 24 | 21114 | MRB III BIO/SCI | MRBIII - Chemical Discharge Tank Replacement | Construction | Jay Surprenant |  | 68452 |  | 68452
| 25 | 20979 | 1025 16TH AVE S | 1025 16th Avenue - Roof Replacement | Construction | Ben Bedock |  | 529750 |  | 529750 | prior year
| 26 | 21035 | LAW SCHOOL | Law School - Roof Ladders | Financial Closeout | Ben Bedock |  | 36108.16 |  | 36108.16 | carryforward
|  | 20179 | LAW SCHOOL | Law School - Fire Alarm System Replacement | Finalized | Bob Grummon |  | -92965.86 |  | -92965.86 | 169023.09
|  | 20924 | FRIST HALL | Frist Hall - Stairwell Roof Replacement | Finalized | Ben Bedock |  | -6070 |  | -6070
[8 empty] | 10171078.44 | 0 | 10171078.44 | 2855229.1123
TRUE
FY 2026 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 20489 | DIVINITY | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Construction | Jay Surprenant | 13263819.6534 | 2369000 | 0 | 2369000
| 2 | 20925 | BLAIR SCHOOL OF MUSIC | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | Construction | Jay Surprenant |  | 1716000 | 0 | 1716000
| 3 | 20962 | VAUGHN HOME | Vaughn Home - Roof Replacement | Design | Ben Bedock |  | 0 | TBD | TBD
| 4 | 20979 | 1025 16TH AVE S | 1025 16th Avenue - Roof Replacement | Construction | Ben Bedock |  | 51438 | 51438 | 102876
| 5 | 21006 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 3 and 6 (Phase 3) | Programming or Planning | Jay Surprenant |  | 0 | TBD | TBD
| 6 | 21051 | MRB III BIO/SCI | MRBIII - 5th Floor Controls | Programming or Planning | Ben Bedock |  | 27500 | 1600000 | 1627500
| 7 | 21067 | GODCHAUX HALL | Godchaux Hall - Phase 2 HVAC Upgrades and Roof Replacement | Bidding | Sean Rewers |  | 0 | 2100000 | 2100000
| 8 | 21127 | MRB III BIO/SCI | MRBIII - Cooling Tower Overhaul | Construction | Jay Surprenant |  | 449020 | 0 | 449020
| 9 | 21155 | SC MOLEC BIOLOGY | SC2 Restroom Upgrades | Programming or Planning | Daniel Capparella |  | 0 | 750000 | 750000
| 10 | 21156 | OLIN HALL | Olin Hall 2nd Floor Chiller | Construction | Nickolaus Corniea |  | 386000 | 340000 | 726000
| 11 | 21157 | COHEN MEMORIAL | Cohen Memorial - Water Intrusion Repair | Design | Jay Surprenant |  | 0 | 25000 | 25000
| 12 | 21165 | WYATT CENTER | Wyatt Center Rotunda Repairs | Programming or Planning | Ben Bedock |  | 0 | TBD | TBD
| 13 | 21173 | 17TH & HORTON | 17th & Horton Elevators Modernization | Programming or Planning | Ben Bedock |  | 25550 | 25550 | 51100
| 14 | 21174 | BUTTRICK HALL | Buttrick Hall - Restore / Replace Exterior Wood Doors and Closures | Not Started | Erin Fry |  | 0 | TBD | TBD
| 15 | 21175 | LAW SCHOOL | Law School Partial Roof Replacement | Programming or Planning | Ben Bedock |  | 0 | TBD | TBD
| 16 | 21176 | LAW SCHOOL | Law School Walkway Replacement | Design | James Moore |  | 0 | 160000 | 160000
| 17 | 21178 | LAW SCHOOL | Law School - Air Compressor Replacement #6 | Construction | Kylie Mignoli |  | 75000 | 75000 | 150000
| 18 | 21189 | BLAIR SCHOOL OF MUSIC | Blair School Legacy VAV Replacement and Duct Encapsulation | Programming or Planning | Ben Bedock |  | 0 | 800000 | 800000
| 19 | 21198 | SC CHEMISTRY | SC7 - AHUs Replacement | Programming or Planning | Sean Rewers |  | 0 | TBD | TBD
| 20 | 21177 | SC MOLEC BIOLOGY | SC2 Molecular Biology HVAC Replacement | Not Started | Daniel Capparella |  | 0 | TBD | TBD
prior year
|  | 10146 | GODCHAUX HALL | Godchaux Hall - HVAC Upgrade | Finalized | Sean Rewers |  | -64230.19 | 0 | -64230.19 | carryforward
|  | 20698 | WILSON HALL | Wilson Hall - Fire Alarm Replacement | Finalized | Sean Rewers |  | -91736.64 | 0 | -91736.64
|  | 20772 | OWEN GRAD MGMT | OGSM Old Mechanical- Slate Roof & Window Replacement | Finalized | Ben Bedock |  | -222611.86 | 0 | -222611.86 | 2855229.1123
|  | 20884 | LAW SCHOOL | Law School - Exterior Window Painting | Finalized | Ben Bedock |  | -195332 | 0 | -195332
|  | 20911 | BUTTRICK HALL | Buttrick Hall - Elevator Upgrades | Finalized | Ben Bedock |  | -6432 | 0 | -6432
[8 empty] | 4519165.31 | 5926988 | 10446153.31 | 5672895.4556
FY 2027 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 20563 | KECK FREE ELECTRON LASER CTR | Keck FEL - Roof Replacement | Not Started | Ben Bedock
| 2 | 20668 | KECK FREE ELECTRON LASER CTR | Keck FEL - Mechanical Upgrades | Design | Sean Rewers |  |  | 3960000
| 3 | 21177 | SC MOLEC BIOLOGY | SC2 Molecular Biology HVAC Replacement | Not Started | Daniel Capparella
|  |  | Divinity (19) | Reading Room (124) Roof - Replace existing roof; |  |  |  |  | 270000
|  | 21073 | Furman Hall (15) | Engineering effort to determine best solution for MEP upgrades |  |  |  |  | 60000
|  | 10150 | Godchaux Hall (22) | Remove and replace 5th and 6th floor roofs. Include area used as patio on the 6th floor (5th floor roof) |  |  |  |  | 390000
|  |  | Sc Molec Biology (Sc2) | Phase 2 of 3: Replace (50) Induction/VAV boxes - entire building |  |  |  |  | 380000
|  | 21005 | Sc Science & Engineering (Sc5) | Phase 2 of 4: Floors 4, 5 and 7; Replace all room induction/FCU units and fume hood controllers |  |  |  |  | 2150000
|  |  | Wilson Hall (125) | Eliminate Steam station in South basement equipment room; Connect to central utilities hot water loop |  |  |  |  | 2410000
|  |  | Sc Science & Engineering (Sc5) | Removing existing chillers and cooling towers (in coordination with SC-6 renovation) |  |  |  |  | 5000000
[8 empty] | 0 | 14620000 | 0 | 0
FY 2028 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
| 1 | 20560 | LAW SCHOOL | Law School - Electrical Gear Replacement - FY23 FR | Design | Sean Rewers | 0
| 2 | 21007 | SC SCIENCE & ENGINEERING | SC5 - HVAC Upgrade Floors 8 and 9 (Phase 4) | Programming or Planning | Jay Surprenant
|  |  | Benson Old Central (16) | Engineering effort resulting in construction documents for replacement of electrical service and replacement of the fire alarm. |  |  |  |  | 80000
|  |  | Blair School Of Music (135) | Elevator 2 Modernization |  |  |  |  | 260000
|  | 21072 | Calhoun Hall (17) | Engineering effort to determine best solution for replacement of AHU-1 and AHU-2 |  |  |  |  | 60000
|  |  | Frist Hall (239) | Complete replacement of Fire alarm panel and devices |  |  |  |  | 190000
|  |  | Godchaux Hall (22) | Complete replacement of Fire alarm panel and devices |  |  |  |  | 390000
|  |  | Furman Hall (15) | AHU-2: Complete replacement of Air Handling Unit including associated piping, valves and controls |  |  |  |  | 2290000
|  |  | Godchaux Hall (22) | Phase 3: Replacement of FCUs from 5th floor down through the Basement. (Includes integration of new FCUs into the BAS system) |  |  |  |  | 2760000
|  |  | Hobbs Hdl (160) | Dock lift Elevator Complete modernization (Controls, fixtures, door equipment, power unit, car enclosure, etc.) |  |  |  |  | 400000
|  |  | Keck Free Electron Laser Ctr (186) | Freight Elevator (#2) Modernization |  |  |  |  | 320000
|  |  | Law School (13) | North West Side 2nd floor entrance; Remove and replace existing patio stone with poured concrete |  |  |  |  | 380000
|  |  | Mrb Iii Bio/Sci (23C) | Phase 5 of 9: 7th Floor Phoenix Controls hardware replacement for lab fume hoods |  |  |  |  | 1720000
|  |  | Peabody Administration (138) | Elevator 1; Complete modernization (Controls, fixtures, door equipment, power unit, etc.) |  |  |  |  | 250000
|  | 21198 | Sc Chemistry (Sc7) | Feasibility Study / Engineering Study to determine best HVAC replacement solution for the 4 main AHUs; Budget: $100k; Project should result in conceptual design including project phasing and conceptual budget. |  |  |  |  | 50000
|  |  | Sc Math (Sc1) | Complete replacement of Fire alarm panel and devices |  |  |  |  | 450000
|  |  | Sc Molec Biology (Sc2) | Phase 3 of 3: Replace (50) Induction/VAV boxes - entire building |  |  |  |  | 2150000
[8 empty] | 0 | 11750000 | 0 | 0
FY 2029 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
0
|  |  | Blair School Of Music (135) | HVAC retro commission to determine scope and funding needed to address HVAC calls throughout the building. |  |  |  |  | 330000
|  |  | Calhoun Hall (17) | Placeholder project to replace AHU-1/AHU-2 resulting from the engineering effort (project 8262) |  |  |  |  | 3190000
|  |  | Calhoun Hall (17) | Replace existing instantaneous water heater |  |  |  |  | 70000
|  |  | Frist Hall (239) | Elevator modernization-Complete modernization (Controls, fixtures, door equipment, power unit, etc.) |  |  |  |  | 270000
|  |  | Godchaux Nursing Annex (131) | AC-3 and Return fan; Refurbish existing equipment with new pan liners, coil, fan wall assembly, remove and replace existing controls |  |  |  |  | 810000
|  |  | Keck Free Electron Laser Ctr (186) | Elevator 1; Complete modernization (Controls, fixtures, door equipment, power unit, etc.) |  |  |  |  | 570000
|  |  | Law School (13) | Elevator 2; Complete modernization (Controls, fixtures, door equipment, power unit, etc.) |  |  |  |  | 280000
|  | 21074 | Law School (13) | Feasibility Study / Engineering effort to determine scope, construction documents and budget pricing for replacement of Air Handling Units and VAV Boxes. |  |  |  |  | 60000
|  |  | Mrb Iii Bio/Sci (23C) | Phase 6 of 9: 6th Floor Phoenix Controls hardware replacement for lab fume hoods |  |  |  |  | 1720000
|  |  | Peabody Administration (138) | Replace 10 existing FCUs throughout the building and 1 existing RTU (DOAS) unit on the roof and existing exhaust fan. |  |  |  |  | 940000
|  |  | Sc Chemistry (Sc7) | Phase 1 of 5 - Floor 9 - Upgrade fume hood controllers, HVAC distribution boxes and controls |  |  |  |  | 1600000
|  |  | Sc Math (Sc1) | Remove and replace one (1) existing exhaust fan (EF-VA-1) for laboratory |  |  |  |  | 50000
|  |  | Sc Math (Sc1) | Remove and replace one (1) existing fans for bathroom exhaust |  |  |  |  | 50000
|  |  | Sc Math (Sc1) | Replace all fan coils in all applicable rooms. |  |  |  |  | 1520000
|  |  | Sc Molec Biology (Sc2) | AHU 2-3: Replace AHU including all associated piping, valves and controls (1st Floor Unit) |  |  |  |  | 2230000
|  |  | Sc Science & Engineering (Sc5) | Phase 4 of 4: Floors 8 and 9; Replace all room induction/FCU units and fume hood controllers |  |  |  |  | 2410000
[8 empty] | 0 | 16100000 | 0 | #REF!
FY 2030 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
0
|  |  | 1025 16Th Ave S (288) | Complete replacement of fire panel and devices. |  |  |  |  | 370000
|  |  | 17Th & Horton (557) | AHU-1: Complete replacement of Air Handling Unit including associated piping, valves and controls. |  |  |  |  | 800000
|  |  | Benson Old Central (16) | Complete system replacement including fire panel and all devices; |  |  |  |  | 410000
|  |  | Blair School Of Music (135) | 3rd floor roof over west addition (Section 5) next to 4th floor penthouse; Replace roof |  |  |  |  | 440000
|  |  | Blair School Of Music (135) | 4th floor over rehearsal hall, Replace roof; Section 4 |  |  |  |  | 180000
|  |  | Blair School Of Music (135) | Roof replacement-2001 addition; West side of building (4th floor penthouse); Section 6 |  |  |  |  | 240000
|  |  | Godchaux Hall (22) | Phase 4: Replacement of Basement AHU (Servicing Basement through 3rd Floor) and Complete needed renovations to Steam/HW plant to accommodate future HW utilities |  |  |  |  | 1990000
|  |  | Keck Free Electron Laser Ctr (186) | Elevator #3; Complete modernization (Controls, fixtures, door equipment, power unit, etc.) |  |  |  |  | 280000
|  |  | Mrb Iii Bio/Sci (23C) | Phase 7 of 9: 5th Floor Phoenix Controls hardware replacement for lab fume hoods |  |  |  |  | 1720000
|  |  | Peabody Administration (138) | Replace electrical switch gear; transformers and electrical panels throughout building; upsize to meet current need |  |  |  |  | 2000000
|  |  | Sc Chemistry (Sc7) | Phase 2 of 5 - Floor 8 - Upgrade fume hood controllers, HVAC distribution boxes and controls |  |  |  |  | 1600000
|  |  | Wyatt Center (142) | Placeholder for HVAC upgrades in the Old side of the building; Replacement of existing Magic Air units and AHU-1Engineering services to determine best solution for replacement of existing Magic Aire FCUs, AHU-1, AHU-3 and AHU-4 |  |  |  |  | 2120000
[8 empty] | 0 | 12150000 | 0 | 0
FY 2031 |  | eB # | Building | Project | Phase | Manager | FRP Collection | Transferred | Estimated | FRP Funding | Remaining
|  |  | 17Th & Horton (557) | AHU-2: Complete replacement of Air Handling Unit including associated piping, valves and controls. |  |  |  |  | 870000
|  |  | Buttrick Hall (24) | Phase 1 of 3 - 1st floor; Retrofit existing light fixtures to LED, install lighting controls and replace original VAV boxes including associated controls and control valves. |  |  |  |  | 1510000
|  |  | E. Bronson Ingram Studio Arts (268) | Replacement of existing controls in VAVs, AHUs and major equipment |  |  |  |  | 950000
|  |  | E. Bronson Ingram Studio Arts (268) | Upgrade / Add lighting to have more adequate lighting for current building usage. |  |  |  |  | 870000
|  |  | Featheringill-Jacobs Hall (27) | Elevator 1 & 2; Complete modernization |  |  |  |  | 500000
|  |  | Godchaux Hall (22) | Elevator #1 modernization |  |  |  |  | 280000
|  |  | Law School (13) | Fall Protection; Replace, relocate and install new Fall protection at various locations. |  |  |  |  | 70000
|  |  | Law School (13) | Remove and replace roof sections 2, 4, and 6 |  |  |  |  | 970000
|  |  | Mrb Iii Bio/Sci (23C) | Elevators #1 - #4 Modernization; Cars #1-4 have to be modernized together since they operate as a group. Complete modernization (Controls, fixtures, door equipment, hoist way equipment, machine, etc.) |  |  |  |  | 1680000
|  |  | Sc Chemistry (Sc7) | Phase 3 of 5 - Floor 7 - Upgrade fume hood controllers, HVAC distribution boxes and controls |  |  |  |  | 1600000
|  |  | Wilson Hall (125) | Phase 1 of 2 - Replace AHU-3, distribution terminal boxes and controls in each space |  |  |  |  | 3820000
[8 empty] | 0 | 13120000 | 0 | 0
Note on E44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Preliminary cost estimates presented in three options. $4M - $5M range.

## 10085 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10085 | 4591 | 0 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Modify/Upgrade Electrical and Grounding | Complete | Finalized | 17500 | 17500
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 22000
|  |  |  | crowhus_06302023_FRP | FX2-1 |  | -4500
|  |  |  | Total transfers from FRP cash |  |  | 17500
|  |  |  | Balance |  |  | 0

## 10098 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10098 | 1627 | CP_400023 | 18200 - Basic Sciences: Office of the Dean | MRB III - 4th Floor - Replace Controls (Phase 2) | Complete | Finalized | 1216485.5 | 1212084.54
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 1216485.5
|  |  |  | crowhus_01302024_FRP | FX2-1 |  | -4400.96
|  |  |  | Total transfers from FRP cash |  |  | 1212084.54
|  |  |  | Balance |  |  | 0

## 10146 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
10146 | 8206 | CP_400025 | 19100 - Nursing: Business Affairs | Godchaux Hall - HVAC Upgrade | Finalized | Sean Rewers | 318057 | 253826.81
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-3 |  | 4900
|  |  |  | FY22 invoices covered by VUSN |  |  | 57200
62100
|  |  |  | crowhus_09302023_FRP | BAC-4 |  | 11500
|  |  |  | crowhus_01302024_FRP | BAC-5 |  | 244457
|  |  |  | FY24 subtotal |  |  | 255957
|  |  |  | crowhus_09302025_FRP | FX2-1 |  | -64230.19
|  |  |  | Balance |  |  | 0

## 20179 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20179 | 36015 | CP_400024 | 17100 - Law: Business Affairs | Law School - Fire Alarm System Replacement | Complete | Finalized | 1445389 | 1352423.14
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 722694.5
|  |  |  | 50% covered by School of Law |  |  | 722694.5
|  |  |  | crowhus_08312024_FRP |  |  | -92965.86
1352423.14
|  |  |  | Total transfers from FRP cash |  |  | 629728.64
|  |  |  | Balance |  |  | 0

## 20336 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20336 | 20075 | CP_400056 | 13000 - Blair: Office of the Dean | Blair School of Music - Elevator #3 Modernization | Complete | Finalized | 327890 | 280600
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 12900
|  |  |  | crowhus_08312022_FRP | BAC-3 |  | 2200
|  |  |  | crowhus_10312022_FRP | BAC-5 |  | 312790
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -47290
|  |  |  | Total transfers from FRP cash |  |  | 280600
|  |  |  | Balance |  |  | 0

## 20431
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20431 | 8084 | CP_400108 | 14000 - Divinity: Office of the Dean | Divinity Air Handling Unit Replacement, (5/6)- Phase 1 | Warranty or Construction Closeout | Hans Mooy | 3800000 | 3542129.41
[9 empty] | 75% | 25%
[9 empty] | FRP | DOS
Funding transfers
|  |  |  | FY22 invoices covered by Divinity |  |  | 46490
|  |  |  | crowhus_09302022_FRP | BAC-5 |  | 937.5 |  | 937.5 | 312.5 | 1250
|  |  |  | crowhus_09302022_FRP | BAC-6 |  | 61425 |  | 61425 | 20475 | 81900
|  |  |  | design to be covered by Dean of Students (DOS) BAC-5 and BAC-6 |  |  | 20787.5
|  |  |  | crowhus_11302022_FRP | BAC-8 |  | 7500 |  | 7500 | 2500 | 10000
|  |  |  | to be covered by Dean of Students (DOS) BAC-8 |  |  | 2500
|  |  |  | crowhus_09302023_FRP | BAC-10 |  | 3660360
All funded by Divinity- split will resume on project 20489- Divinity AHU 1N
3800000
|  |  |  | Total transfers from FRP cash |  |  | 3730222.5
|  |  |  | Balance |  |  | 0

## 20478
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20478 | 8672 | CP_400182 | 12000 - Arts and Science: Office of the Dean | Bryan Building - Swing Space Renovation - A&S Planning | Warranty or Construction Closeout | Cathy Bartlett | 2790000 | 2652824.48
[9 empty] | FRP | A&S
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 12100 |  | 12100 | 6900 | 19000
|  |  |  | design to be covered by A&S |  |  | 6900
|  |  |  | crowhus_03312023_FRP | BAC-2 |  | 69000 |  | 69000 | 32500 | 101500
|  |  |  | design to be covered by A&S |  |  | 32500
|  |  |  | crowhus_08082023_FRP | BAC-3 |  | 1028900 |  | 1028900 | 1640600 | 2669500
|  |  |  | work to be covered by A&S |  |  | 1640600
[7 empty] | 2790000 |  | 1110000 | 1680000
|  |  |  | Total transfers from FRP cash |  |  | 1110000
|  |  |  | Balance |  |  | 0

## 20489
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20489 | 8051 | CP_400183 | 14000 - Divinity: Office of the Dean | Divinity Air Handling Unit Replacement,(1/3) - Phase 2 with Benton - FY26 | Construction | Jay Surprenant | 3600000 | 194523.21
|  |  |  | Funding transfers |  |  | Divinity | Dean of Students
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 26500
|  |  |  | crowhus_05312025_FRP | BAC-3 |  | 304500
|  |  |  | crowhus_08312025_FRP | BAC-4 |  | 2369000 | 900000
|  |  |  | Total transfers from FRP cash |  |  | 2700000 | 900000
[7 empty] | 75% | 25%
|  |  |  | Balance |  |  |  | 0

## 20497 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20497 | 529 | CP_400127 | 21000 - Peabody College: Office of the Dean | Jesup - Roof Replacement | Complete | Finalized | 456850 | 412000
Funding transfers
|  |  |  | crowhus_07272022_FRP | 2022-07-27 |  | 79415.5
|  |  |  | FY22 invoices covered by Peabody |  |  | 377434.5
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -44850
|  |  |  | Total transfers from FRP cash |  |  | 412000
|  |  |  | Balance |  |  | 0

## 20506 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20506 | 1170 | CP_400192 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Window Replacement | Complete | Finalized | 344155.26 | 307776.26
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 344155.26
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -36379
|  |  |  | Total transfers from FRP cash |  |  | 307776.26
|  |  |  | Balance |  |  | 0

## 20562 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20562 | 4564 | CP_400175 | 21000 - Peabody College: Office of the Dean | Wyatt Center - VAV Replacement | Complete | Finalized | 400000 | 362559.64
Funding transfers
|  |  |  | crowhus_12312022_FRP | BAC-1 |  | 405791
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -43231.36
|  |  |  | Total transfers from FRP cash |  |  | 362559.64
|  |  |  | Balance |  |  | 0

## 20566 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20566 | 20054 | CP_400151 | 12000 - Arts and Science: Office of the Dean | SC Chemistry (SC7) - Elevator 1 & 2 Modernization | Complete | Finalized | 781870 | 722586.68
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 17050
|  |  |  | crowhus_11302022_FRP | BAC-2 |  | 764820
|  |  |  | crowhus_02292024_FRP | FX |  | -59283.32
|  |  |  | Total transfers from FRP cash |  |  | 722586.68
|  |  |  | Balance |  |  | 0

## 20573 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20573 | 8047 | CP_400185 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Roof Replacement | Complete | Finalized | 1232681 | 1113460
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 1232681
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -119221
|  |  |  | Total transfers from FRP cash |  |  | 1113460
|  |  |  | Balance |  |  | 0

## 20574 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20574 | 8145 | CP_400164 | 18200 - Basic Sciences: Office of the Dean | MRB III - Steam Coil Replacement | Complete | Finalized | 218202 | 195665
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 218202
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -22537
|  |  |  | Total transfers from FRP cash |  |  | 195665
|  |  |  | Balance |  |  | 0

## 20577
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20577 | 8146 | CP_400154 | 13000 - Blair: Office of the Dean | Blair School of Music - AHU - 1 Replacement - Phase 1 - FY25 | Construction | Jay Surprenant | 1300000 | 1104104.21
Funding transfers
|  |  |  | crowhus_08312022_FRP | BAC-1 |  | 53750
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 169250
|  |  |  | crowhus_10312024_FRP | BAC-4 |  | 1077000
|  |  |  | Total transfers from FRP cash |  |  | 1300000
|  |  |  | Balance |  |  | 0

## 20644 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20644 | 8241 | CP_400171 | 21000 - Peabody College: Office of the Dean | Peabody Administration - Envelope Repairs | Complete | Finalized | 630554 | 571789
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2050
|  |  |  | crowhus_02282023_FRP | BAC-2 |  | 628504
|  |  |  | crowhus_03312024_FRP | FX2-1 |  | -58765
|  |  |  | Total transfers from FRP cash |  |  | 571789
|  |  |  | Balance |  |  | 0

## 20645 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20645 | 8239 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Old Central - Replace Soffit and Doors | Complete | Finalized | 125875 | 114350
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-1 |  | 125875
|  |  |  | crowhus_04302024_FRP | FX2-1 |  | -11525
|  |  |  | Total transfers from FRP cash |  |  | 114350
|  |  |  | Balance |  |  | 0

## 20667
Project Status'!A1
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20667 | 8168 | CP_400160 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Mechanical and Electrical Upgrades | Construction | Kylie Mignoli | 1545360 | 1384276.78
Funding transfers
|  |  |  | crowhus_09302022_FRP | BAC-1 |  | 135000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | crowhus_12312024_FRP | BAC-4 |  | 1398860
|  |  |  | Total transfers from FRP cash |  |  | 1545360
|  |  |  | Balance |  |  | 0

## 20668
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20668 | 8151 | CP_400163 | 15000 - Engineering: Office of the Dean | Keck FEL - Mechanical Upgrades | Design | Sean Rewers | 231433 | 116143
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 195000
|  |  |  | crowhus_12312022_FRP | BAC-3 |  | 11500
|  |  |  | crowhus_10312023_FRP | BAC-4 |  | 24933
|  |  |  | Total transfers from FRP cash |  |  | 231433
|  |  |  | Balance |  |  | 0

## 20698 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20698 | 1138 | CP_400168 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Fire Alarm Replacement | Finalized | Sean Rewers | 678513 | 586776.36
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 24500
|  |  |  | crowhus_10312022_FRP | BAC-2 |  | 450
|  |  |  | crowhus_05312023_FRP | BAC-3 |  | 4300
|  |  |  | crowhus_01302024_FRP | BAC-4 | ` | 649263
|  |  |  | crowhus_09302025_FRP | FX2-1 |  | -91736.64
|  |  |  | Total transfers from FRP cash |  |  | 586776.36
|  |  |  | Balance |  |  | 0

## 20700 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20700 | 851 | 0 | 12000 - Arts and Science: Office of the Dean | SC-7 Chemistry - SG-1 Removal and Connection to Central Plant Steam | Complete | Finalized | 80000 | 85576.77
Funding transfers
|  |  |  | crowhus_11302022_FRP | BAC-1 |  | 2500
|  |  |  | crowhus_02282023_FRP | BAC-1 |  | 77123
|  |  |  | crowhus_09302023_FRP | BAC-5 |  | 5954
|  |  |  | Total transfers from FRP cash |  |  | 85577
|  |  |  | Balance |  |  | -0.23

## 20701
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20701 | 4399 | CP_400198 | 12000 - Arts and Science: Office of the Dean | SC-5 - Chemical Discharge Replacement | Finalized | Sean Rewers | 499093 | 447535.86
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 499093
|  |  |  | crowhus_01312026_FRP | FX2-1 |  | -51557.14
|  |  |  | Total transfers from FRP cash |  |  | 447535.86
|  |  |  | Balance |  |  | 0

## 20702 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20702 | 8432 | CP_400165 | 21000 - Peabody College: Office of the Dean | Wyatt Center - Elevator #2 Modernization | Complete | Finalized | 225791 | 209419
Funding transfers
|  |  |  | crowhus_10312022_FRP | BAC-1 |  | 13550
|  |  |  | crowhus_12312022_FRP | BAC-2 |  | 225791
|  |  |  | crowhus_02292024_FRP | FX |  | -29922
|  |  |  | Total transfers from FRP cash |  |  | 209419
|  |  |  | Balance |  |  | 0

## 20718 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20718 | 8608 | CP_400174 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - 3rd Floor Inequality Renovations | Complete | Finalized | 715000 | 656784.6
Funding transfers
|  |  |  | crowhus_05312023_FRP | BAC-3 (partial) |  | 96166
VAV controls only
|  |  |  | work to be covered by A&S |  |  | 618834
715000
|  |  |  | Total transfers from FRP cash |  |  | 96166
|  |  |  | Balance |  |  | 0

## 20723
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20723 | 1628 | CP_400187 | 18200 - Basic Sciences: Office of the Dean | MRB III - 9th Floor (with 4 ,5 & 8) - Replace Controls (Phase 3) | Construction | Jay Surprenant | 1700000 | 1146822.02
Funding transfers
|  |  |  | crowhus_02282023_FRP |  |  | 24500
|  |  |  | crowhus_03312023_FRP |  |  | 136000
|  |  |  | crowhus_10312024_FRP |  |  | 1539500
|  |  |  | Total transfers from FRP cash |  |  | 1700000
|  |  |  | Balance |  |  | 0

## 20724
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20724 | 8557 | CP_400178 | 13000 - Blair: Office of the Dean | Blair School of Music - Steam Line - FY 23 | Financial Closeout | Hans Mooy | 1987500 | 1839258.28
Funding transfers
|  |  |  | crowhus_01312023_FRP | BAC-1 |  | 23400
|  |  |  | crowhus_12192023_FRP | BAC-2 |  | 1964100
|  |  |  | crowhus_01312026_FRP | FX2-1 |  | -148241.72
|  |  |  | Total transfers from FRP cash |  |  | 1839258.28
|  |  |  | Balance |  |  | 0

## 20735 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20735 | 8226 | 0 | 20000 - Owen: Office of the Dean | Owen - Roof Replacement (Third Level) | Complete | Finalized | 300000 | 276500
Funding transfers
|  |  |  | crowhus_04302023_FRP | BAC-1 |  | 300000
|  |  |  | crowhus_06302024_FRP | FX2-1 |  | -23500
|  |  |  | Total transfers from FRP cash |  |  | 276500
|  |  |  | Balance |  |  | 0

## 20767
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20767 | 8673 | CP_400242 | 21000 - Peabody College: Office of the Dean | Six Magnolia Circle - Foundation Repairs | Warranty or Construction Closeout | Jay Surprenant | 148299 | 125699
Funding transfers
|  |  |  | crowhus_03312024_FRP | BAC-1 |  | 148299
|  |  |  | Total transfers from FRP cash |  |  | 148299
|  |  |  | Balance |  |  | 0

## 20771 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20771 | 8674 | 0 | 12000 - Arts and Science: Office of the Dean | SC4 - Interstitial Space HVAC Modifications | Complete | Finalized | 25000 | 17972
Funding transfers
|  |  |  | crowhus_03312023_FRP | BAC-1 |  | 19297
|  |  |  | crowhus_04302023_FRP | BAC-2 |  | 5700
|  |  |  | crowhus_10312023_FRP | FX2-1 |  | -7025
|  |  |  | Total transfers from FRP cash |  |  | 17972
|  |  |  | Balance |  |  | 0

## 20792 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20792 | 1035 | CP_400206 | 17100 - Law: Business Affairs | Law School - Sections 1, 2, & 3 Roof Replacement | Complete | Finalized | 400000 | 450775
Funding transfers
|  |  |  | crowhus_06302023_FRP | BAC-1 |  | 483440
|  |  |  | crowhus_02292024_FRP | FX |  | -32665
|  |  |  | Total transfers from FRP cash |  |  | 450775
|  |  |  | Balance |  |  | 0

## 20831 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20831 | 8230 | 0 | 12000 - Arts and Science: Office of the Dean | SC6 - HVAC Upgrades - Feasibility Study | Complete | Finalized | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20832 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20832 | 8220 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - HVAC Replacement | Complete | Finalized | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20833 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20833 | 8215 | 0 | 12000 - Arts and Science: Office of the Dean | SC5 - HVAC Replacement (Design Services) | Complete | Finalized | 24000 | 24000
Funding transfers
|  |  |  | crowhus_09302023_FRP | BAC-1 |  | 24000
|  |  |  | Total transfers from FRP cash |  |  | 24000
|  |  |  | Balance |  |  | 0

## 20772 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20772 | 8675 | CP_400235 | 20100 - Owen: Business Affairs | OGSM Old Mechanical- Slate Roof & Window Replacement | Finalized | Ben Bedock | 3200000 | 2977388.14
Funding transfers
|  |  |  | crowhus_06302024_FRP | BAC-1 |  | 1600000
|  |  |  | crowhus_07312024_FRP | BAC-1 |  | 1600000
|  |  |  | crowhus_08312025_FRP | FX2-1 |  | -222611.86
|  |  |  | Total transfers from FRP cash |  |  | 2977388.14
|  |  |  | Balance |  |  | 0

## 20811
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20811 | 8729 | CP_400224 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Retaining Wall Repair | Finalized | Ben Bedock | 285233.27 | 123523.71
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-1 |  | 285233.27
|  |  |  | crowhus_01312026_FRP | FX2-1 |  | -161709.56
|  |  |  | Total transfers from FRP cash |  |  | 123523.71
|  |  |  | Balance |  |  | 0
Original budget (BAC-1) for $2,640 set up as a Facilities capital project, owning org 37000. It has been determined this is an FRP project and will be assigned to Peabody. Owning org has been updated in Oracle.

## 20812
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20812 | 8923 | CP_400282 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Patio Repairs | Construction | Sean Rewers | 486135 | 377024.69
Funding transfers
|  |  |  | crowhus_08312024_FRP | BAC-1 |  | 4500
|  |  |  | crowhus_08312024_FRP | BAC-2 |  | 34000
|  |  |  | crowhus_04302025_FRP | BAC-3 |  | 447635
|  |  |  | Total transfers from FRP cash |  |  | 486135
|  |  |  | Balance |  |  | 0

## 20857
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20857 | 8427 | CP_400227 | 21000 - Peabody College: Office of the Dean | One Magnolia Circle - Elevator Modernization | Construction Closeout | Ben Bedock | 499184 | 481346.67
Funding transfers
|  |  |  | crowhus_10312023_FRP | BAC-1 |  | 17600
|  |  |  | crowhus_01302024_FRP | BAC-2 |  | 4000
|  |  |  | crowhus_03312024_FRP | BAC-3 |  | 477584
|  |  |  | Total transfers from FRP cash |  |  | 499184
|  |  |  | Balance |  |  | 0

## 20884 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20884 | 8807 | CP_400251 | 17000 - Law: Office of the Dean | Law School - Exterior Window Painting | Finalized | Ben Bedock | 675650 | 480318
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-3 |  | 675650
|  |  |  | crowhus_09302025_FRP | FX2-1 |  | -195332
|  |  |  | Total transfers from FRP cash |  |  | 480318
|  |  |  | Balance |  |  | 0

## 20885
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20885 | 8676 | 0 | 12000 - Arts and Science: Office of the Dean | NMR - Replace Air Compressors | Financial Closeout | Sean Rewers | 143053.4 | 123743.89
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-2 |  | 98341
|  |  |  | crowhus_05312024_FRP | BAC-3 |  | 14712.4
|  |  |  | crowhus_09302024_FRP | BAC-4 |  | 30000
|  |  |  | crowhus_01312026_FRP | FX2-1 |  | -19309.51
|  |  |  | Total transfers from FRP cash |  |  | 123743.89
|  |  |  | Balance |  |  | 0

## 20911 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20911 | 8819 | 0 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - Elevator Upgrades | Finalized | Ben Bedock | 61045 | 54613
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 56945
|  |  |  | crowhus_09302025_FRP | FX2-2 |  | -6432
|  |  |  | Total transfers from FRP cash |  |  | 54613
|  |  |  | Balance |  |  | 0

## 20912
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20912 | 8822 | 0 | 12000 - Arts and Science: Office of the Dean | Benson Hall - Elevator Upgrades | Financial Closeout | Ben Bedock | 59798 | 53366
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 55698
|  |  |  | Total transfers from FRP cash |  |  | 59798
|  |  |  | Balance |  |  | 0

## 20913
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20913 | 8818 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Elevator Upgrades | Financial Closeout | Ben Bedock | 96612 | 86900
Funding transfers
|  |  |  | crowhus_02292024_FRP | BAC-1 |  | 4100
|  |  |  | crowhus_03312024_FRP | BAC-2 |  | 92512
|  |  |  | Total transfers from FRP cash |  |  | 96612
|  |  |  | Balance |  |  | 0

## 20922
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20922 | 8720 | CP_400263 | 12000 - Arts and Science: Office of the Dean | Vaughn Home - Exterior Improvements | Warranty or Construction Closeout | Jay Surprenant | 197150 | 170000
Funding transfers
|  |  |  | crowhus_05312024_FRP | BAC-1 |  | 197150
|  |  |  | Total transfers from FRP cash |  |  | 197150
|  |  |  | Balance |  |  | 0

## 20924 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20924 | 8737 | 0 | 19000 - Nursing: Office of the Dean | Frist Hall - Stairwell Roof Replacement | Finalized | Ben Bedock | 30570 | 24500
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-1 |  | 30570
|  |  |  | crowhus_06302025_FRP | FX2-1 |  | -6070
|  |  |  | Total transfers from FRP cash |  |  | 24500
|  |  |  | Balance |  |  | 0

## 20925
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20925 | 8260 | CP_400326 | 13000 - Blair: Office of the Dean | Blair School of Music - AHU 2/3 Replacement - Phase 2 - FY26 | Construction | Jay Surprenant | 2125000 | 287445
Funding transfers
|  |  |  | crowhus_05312025_FRP | BAC-1 |  | 409000
|  |  |  | crowhus_08312025_FRP | BAC-2 |  | 1716000
|  |  |  | Total transfers from FRP cash |  |  | 2125000
|  |  |  | Balance |  |  | 0

## 20936
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20936 | 8814 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - Lighting Retrofit for 103 and 126 | Warranty or Construction Closeout | Jay Surprenant | 404655.91 | 357255.91
Funding transfers
|  |  |  | crowhus_04302024_FRP | BAC-1 |  | 404655.91
|  |  |  | Total transfers from FRP cash |  |  | 404655.91
|  |  |  | Balance |  |  | 0

## 20940
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20940 | 8412 | CP_400291 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Security System Replacement | Financial Closeout | Sean Rewers | 309548.64 | 298567.26
Funding transfers
|  |  |  | crowhus_10312024_FRP | BAC-1 |  | 294789
|  |  |  | crowhus_01312025_FRP | BAC-3 |  | 14759.64
|  |  |  | Total transfers from FRP cash |  |  | 309548.64
|  |  |  | Balance |  |  | 0

## 20945
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20945 | 8905 | 0 | 10000 - Chancellor | Seigenthaler Building - HVAC Improvements | Finalized | Sean Rewers | 99000 | 70200
Funding transfers
|  |  |  | crowhus_03312024_FRP | BAC-1 |  | 99000
|  |  |  | crowhus_01312026_FRP | FX2-1 |  | -28800
|  |  |  | Total transfers from FRP cash |  |  | 70200
|  |  |  | Balance |  |  | 0

## 20958
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20958 | 1642 | CP_400256 | 12000 - Arts and Science: Office of the Dean | Furman Hall - Elevator Modernization | Construction Closeout | Ben Bedock | 261629 | 137776.91
Funding transfers
|  |  |  | crowhus_05312024_FRP | BAC-1 |  | 18175
|  |  |  | crowhus_08312024_FRP | BAC-2 |  | 243454
|  |  |  | Total transfers from FRP cash |  |  | 261629
|  |  |  | Balance |  |  | 0

## 20962
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20962 | 8754 | 0 | 12000 - Arts and Science: Office of the Dean | Vaughn Home - Roof Replacement | Design | Ben Bedock | 1800 | 1800
Funding transfers
|  |  |  | crowhus_01312025_FRP | BAC-1 |  | 1800
|  |  |  | Total transfers from FRP cash |  |  | 1800
|  |  |  | Balance |  |  | 0

## 20979
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20979 | 9 | CP_400330 | 15000 - Engineering: Office of the Dean | 1025 16th Avenue - Roof Replacement | Construction | Ben Bedock | 581188 | 365000
Funding transfers
|  |  |  | crowhus_06302025_FRP | BAC-1 |  | 529750
|  |  |  | crowhus_01312026_FRP | BAC-2 |  | 51438
|  |  |  | Total transfers from FRP cash |  |  | 581188
|  |  |  | Balance |  |  | 0

## 20982
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20982 | 8442 | CP_400270 | 17100 - Law: Business Affairs | Law School - Elevator 1 Modernization | Construction Closeout | Ben Bedock | 272000 | 246321
Funding transfers
|  |  |  | crowhus_06302024_FRP | BAC-1 |  | 18175
|  |  |  | crowhus_10312024_FRP | BAC-2 |  | 253825
|  |  |  | Total transfers from FRP cash |  |  | 272000
|  |  |  | Balance |  |  | 0

## 20984
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
20984 | 8712 | 0 | 12000 - Arts and Science: Office of the Dean | Wilson Hall - 1st Floor Urinal Replacement | Financial Closeout | Hans Mooy | 167000 | 136652
Funding transfers
|  |  |  | crowhus_09302024_FRP | BAC-1 |  | 167000
|  |  |  | Total transfers from FRP cash |  |  | 167000
|  |  |  | Balance |  |  | 0

## 21004
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21004 | 1010 | CP_400332 | 12100 - Arts and Science: Business Affairs | SC5 - HVAC Upgrade Floors 1 and 2 (Phase 1) | Construction | Jay Surprenant | 992453 | 37400
Funding transfers
|  |  |  | crowhus_10312024_FRP | BAC-1 |  | 54000
|  |  |  | crowhus_05312025_FRP | BAC-2 |  | 938453
|  |  |  | Total transfers from FRP cash |  |  | 992453
|  |  |  | Balance |  |  | 0

## 21010
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21010 | 0 | CP_400312 | 15000 - Engineering: Office of the Dean | Featheringill-Jacobs Hall - Hot Water Tank Replacement | Financial Closeout | Sean Rewers | 126024 | 112824.84
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 126024
|  |  |  | crowhus_01312026_FRP | FX2-1 |  | -13199.16
|  |  |  | Total transfers from FRP cash |  |  | 112824.84
|  |  |  | Balance |  |  | 0

## 21035
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21035 | 0 | 0 | 17100 - Law: Business Affairs | Law School - Roof Ladders | Financial Closeout | Ben Bedock | 36108.16 | 32589.24
Funding transfers
|  |  |  | crowhus_05312025_FRP | BAC-1 |  | 36108.16
|  |  |  | Total transfers from FRP cash |  |  | 36108.16
|  |  |  | Balance |  |  | 0

## 21051
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21051 | 8784 | CP_400344 | 18200 - Basic Sciences: Office of the Dean | MRBIII - 5th Floor Controls | Programming or Planning | Ben Bedock | 27500 | 0
Funding transfers
|  |  |  | crowhus_11302025_FRP | BAC-1 |  | 27500
|  |  |  | Total transfers from FRP cash |  |  | 27500
|  |  |  | Balance |  |  | 0

## 21066
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21066 | 0 | CP_400314 | 12000 - Arts and Science: Office of the Dean | SC2 - MEP Feasibility Study | Programming or Planning | Sean Rewers | 29160 | 24786
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 29160
|  |  |  | Total transfers from FRP cash |  |  | 29160
|  |  |  | Balance |  |  | 0

## 21067
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21067 | 0 | CP_400311 | 19000 - Nursing: Office of the Dean | Godchaux Hall - Phase 2 HVAC Upgrades and Roof Replacement | Bidding | Sean Rewers | 46600 | 22810
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 33600
|  |  |  | crowhus_02282025_FRP | BAC-2 |  | 13000
|  |  |  | Total transfers from FRP cash |  |  | 46600
|  |  |  | Balance |  |  | 0

## 21068
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21068 | 0 | 0 | 12000 - Arts and Science: Office of the Dean | Buttrick Hall - Insulate First Floor Slab | Construction Closeout | Jay Surprenant | 34837.4 | 24737.4
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 34837.4
|  |  |  | Total transfers from FRP cash |  |  | 34837.4
|  |  |  | Balance |  |  | 0

## 21070
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21070 | 8733 | 0 | 15000 - Engineering: Office of the Dean | Olin Hall - Exterior Facade Cleaning | Financial Closeout | Ben Bedock | 392042.1 | 308101
Funding transfers
|  |  |  | crowhus_03312025_FRP | BAC-1 |  | 392042.1
|  |  |  | Total transfers from FRP cash |  |  | 392042.1
|  |  |  | Balance |  |  | 0

## 21071
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21071 | 0 | CP_400313 | 12000 - Arts and Science: Office of the Dean | SC1 - MEP Feasibility Study | Programming or Planning | Sean Rewers | 19440 | 16524
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 19440
|  |  |  | Total transfers from FRP cash |  |  | 19440
|  |  |  | Balance |  |  | 0

## 21094
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21094 | 0 | 0 | 17000 - Law: Office of the Dean | Godchaux Hall - Replace Fire Pump | Financial Closeout | Sean Rewers | 87500 | 48640
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 87500
|  |  |  | Total transfers from FRP cash |  |  | 87500
|  |  |  | Balance |  |  | 0

## 21108 (hidden)
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21108 | 0 | 0 | 19100 - Nursing: Business Affairs | 1025 16th Avenue - Electrical and HVAC Study | Finalized | Sean Rewers | 5000 | 5000
Funding transfers
|  |  |  | crowhus_02282025_FRP | BAC-1 |  | 5000
|  |  |  | Total transfers from FRP cash |  |  | 5000
|  |  |  | Balance |  |  | 0

## 21113
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21113 | 0 | 0 | 15000 - Engineering: Office of the Dean | MRBIII - Lecture Hall V1220 Lighting Upgrade | Construction | Jay Surprenant | 82125 | 0
Funding transfers
|  |  |  | crowhus_06302025_FRP | BAC-1 |  | 82125
|  |  |  | Total transfers from FRP cash |  |  | 82125
|  |  |  | Balance |  |  | 0

## 21114
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21114 | 0 | 0 | 18200 - Basic Sciences: Office of the Dean | MRBIII - Chemical Discharge Tank Replacement | Construction | Jay Surprenant | 68452 | 0
Funding transfers
|  |  |  | crowhus_05312025_FRP | BAC-1 |  | 68452
|  |  |  | Total transfers from FRP cash |  |  | 68452
|  |  |  | Balance |  |  | 0

## 21127
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21127 | 0 | CP_400334 | 18200 - Basic Sciences: Office of the Dean | MRBIII - Cooling Tower Overhaul | Construction | Jay Surprenant | 449020 | 0
Funding transfers
|  |  |  | crowhus_07312025_FRP | BAC-1 |  | 449020
|  |  |  | Total transfers from FRP cash |  |  | 449020
|  |  |  | Balance |  |  | 0

## 21156
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21156 | 0 | CP_400337 | 15000 - Engineering: Office of the Dean | Olin Hall 2nd Floor Chiller | Construction | Nickolaus Corniea | 386000 | 10800
Funding transfers
|  |  |  | crowhus_11302025_FRP | BAC-1 |  | 386000
|  |  |  | Total transfers from FRP cash |  |  | 386000
|  |  |  | Balance |  |  | 0

## 21173
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21173 | 0 | CP_400343 | 22000 - College of Connected Computing: Office of the Dean | 17th & Horton Elevators Modernization | Programming or Planning | Ben Bedock | 25550 | 0
Funding transfers
|  |  |  | crowhus_11302025_FRP | BAC-1 |  | 25550
|  |  |  | Total transfers from FRP cash |  |  | 25550
|  |  |  | Balance |  |  | 0

## 21178
Project Status'!A1
eBuilder | AiM | Oracle | School | Project | Phase | Manager | Approved budget | Final costs
21178 | 0 | 0 | 17100 - Law: Business Affairs | Law School - Air Compressor Replacement #6 | Construction | Kylie Mignoli | 75000 | 2500
Funding transfers
|  |  |  | crowhus_11302025_FRP | BAC-1 |  | 75000
|  |  |  | Total transfers from FRP cash |  |  | 75000
|  |  |  | Balance |  |  | 0

## JE LOG_FY26
Project Status'!A1
Completed journal entries
| Sources |  | Journal entries to be processed next
|  | 13263820 | tbd | 0
| Total sources | 13263820
Uses
| crowhus_07312025_FRP | 449020
| crowhus_08312025_FRP | 3862388.14
| crowhus_09302025_FRP | -357730.83
| crowhus_11302025_FRP | 514050
| crowhus_12312025_FRP | 0
| crowhus_01312026_FRP | -371379.09
0
0
0
0
0
| Total Uses | 4096348.22
| plus carryforward | 2855230
| (less) TBD | 0 |  |  | DB: | CR:
2369000
| Balance | 12022701.78 |  |  |  | 1716000
222611.86
[5 empty] | 222611.86 | 4085000 | 4307611.86
3862388.14
[5 empty] | DB: | CR:
386000
75000
27500
25550
[5 empty] | 0 | 514050 | 1028100
514050
[5 empty] | DB: | CR:
51438
51557.14
161709.56
28800
[5 empty] | 242066.7 | 51438 | 293504.7
-190628.7

## JE LOG_FY25
Project Status'!A1
Completed journal entries
| Sources |  | Journal entries to be processed next
| crowhus_08072023_FRP | 12857284.4623 | tbd | 0
| Total sources | 12857284.4623
Uses
| crowhus_07312024_FRP | 1600000
| crowhus_08312024_FRP | 188988.14
| crowhus_09302024_FRP | 197000
| crowhus_10312024_FRP | 3219114
| crowhus_12312024_FRP | 1398860
| crowhus_01312025_FRP | 16559.64
| crowhus_02282025_FRP | 348561.4
| crowhus_03312025_FRP | 392042.1
| crowhus_04302025_FRP | 447635
| crowhus_05312025_FRP | 1756513.16
| crowhus_06302025_FRP | 605805
| Total Uses | 10171078.44
| plus carryforward | 169023.09
| (less) TBD | 0 |  |  | DB: | CR:
38500
| Balance | 2855229.1123 |  |  |  | 243454
92965.86
[5 empty] | 92965.86 | 281954 | 374919.86
188988.14
[5 empty] | DB: | CR:
1800
14759.64
33119.28
[5 empty] | 33119.28 | 16559.64 | 49678.92
-16559.64
[5 empty] | DB: | CR:
[5 empty] | 5000 | 34837.4
[5 empty] | 13000 | 19440
[5 empty] | 19440 | 29160
[5 empty] | 29160 | 5000
[5 empty] | 33600 | 126024
[5 empty] | 34837.4 | 13000
[5 empty] | 87500 | 33600
[5 empty] | 126024 | 87500
[5 empty] | 348561.4 | 348561.4 | 697122.8
0
[5 empty] | DB: | CR:
447635
447635
[5 empty] | 447635 | 447635 | 895270
0
[5 empty] | DB: | CR:
529750
82125
6070
[5 empty] | 6070 | 611875 | 617945
605805

## JE LOG_FY24
Project Status'!A1
Completed journal entries
Sources
| crowhus_08072023_FRP | 11029283.29
| Total sources | 11029283.29
Uses
| crowhus_08082023_FRP | 1028900
| crowhus_09302023_FRP | 3749814
| crowhus_10312023_FRP | -45721
| crowhus_12192023_FRP | 1964100
| crowhus_01302024_FRP | 893319.04
| crowhus_02292024_FRP | -11229.32
| crowhus_03312024_FRP | 638993.64
| crowhus_04302024_FRP | 1384584.18
| crowhus_05312024_FRP | 230037.4
| crowhus_06302024_FRP | 1594675
| Total Uses | 11427472.94
| plus carryforward | 567212.74
| (less) TBD | 0
| Balance | 169023.09 | DB: | CR:
|  |  | 7025 | 24933
|  |  | 36379 | 17600
44850
|  |  | 88254 | 42533 | 130787
-45721
|  |  | DB: | CR:
|  |  | 1964100 | 1964100
|  |  | 1964100 | 1964100
|  |  | 3928200 | 3928200
0
|  |  | DB: | CR:
649263
244457
4000
4400.96
|  |  | 4400.96 | 897720 | 902120.96
893319.04
|  |  | DB: | CR:
12300
98341
59283.32
29922
32665
|  |  | 121870.32 | 110641 | 232511.32
-11229.32
|  |  | DB: | CR:
148299
|  |  | 47290 | 477584
|  |  | 43231.36 | 56945
|  |  | 119221 | 55698
|  |  | 22537 | 92512
|  |  | 58765 | 99000
|  |  | 291044.36 | 930038 | 1221082.36
638993.64
|  |  | DB: | CR:
285233.27
675650
30570
404655.91
11525
|  |  | 11525 | 1396109.18 | 1407634.18
1384584.18
|  |  | 460074.8 | 230037.4
|  |  | DB: | CR:
18175
1600000
23500
|  |  | 23500 | 1618175 | 1641675
1594675

## JE LOG_FY23
Project Status'!A1
Completed journal entries
Sources
| crowhus_07262022_FRP | 9364499
| Total sources | 9364499
Uses
| crowhus_07272022_FRP | 2018595.5
| crowhus_08312022_FRP | 85900
| crowhus_09302022_FRP | 197362.5
| crowhus_10312022_FRP | 791392
| crowhus_11302022_FRP | 776870
| crowhus_12312022_FRP | 823832
| crowhus_01312023_FRP | 1294681
| crowhus_02282023_FRP | 730127
| crowhus_03312023_FRP | 1067545.26
| crowhus_04302023_FRP | 305700
| crowhus_05312023_FRP | 226341
| crowhus_06302023_FRP | 478940
| Total Uses | 8797286.26
| Balance | 567212.74

## lookup
eBuilder | Summary
10000 - Chancellor | Other
12000 - Arts and Science: Office of the Dean | Arts & Science
12100 - Arts and Science: Business Affairs | Arts & Science
13000 - Blair: Office of the Dean | Blair
14000 - Divinity: Office of the Dean | Divinity
15000 - Engineering: Office of the Dean | Engineering
17000 - Law: Office of the Dean | Law
17000 - Law School: Office of the Dean | Law
17100 - Law: Business Affairs | Law
18200 - Basic Sciences: Office of the Dean | School of Medicine
19000 - Nursing: Office of the Dean | School of Nursing
19100 - Nursing: Business Affairs | School of Nursing
20000 - Owen: Office of the Dean | Owen
20100 - Owen: Business Affairs | Owen
21000 - Peabody College: Office of the Dean | Peabody
22000 - College of Connected Computing: Office of the Dean | College of Connected Computing

## PUC GSF (hidden)
Financial Unit | CBO | VC Rollup | FY23 GSF | In the Program?
10000 - Office of the Chancellor | Kwasi Appiah | Chancellor | 5849.5212 | No
11000 - Academic Affairs: Office of the Provost | Jennifer Bischoff | Provost | 26280.6212 | No
12000 - Arts and Science: Office of the Dean | Josh Brewer | Provost | 1075461.7321 | Yes
13000 - Blair: Office of the Dean | Kathryn Dudley | Provost | 121421.4269 | Yes
14000 - Divinity: Office of the Dean | Kathryn Dudley | Provost | 57814.7309 | Yes
15000 - Engineering: Office of the Dean | Hector Silva | Provost | 537962.3327 | Yes
16000 - Graduate Education | Jennifer Gourley | Provost | 6753.6107 | No
17000 - Law: Office of the Dean | Bonnie Bielec | Provost | 120155.4846 | Yes
18200 - Basic Sciences: Office of the Dean | Claudia Paz | Provost | 280022.3999 | Yes
18500 - Health Sciences Education: Office of the Dean | Jane Zubulake | Provost | 42799 | No
19000 - Nursing: Office of the Dean | Jane Zubulake | Provost | 106166.7 | Yes
20000 - Owen: Office of the Dean | Stella Vazna | Provost | 59008.3617 | Yes
21000 - Peabody College: Office of the Dean | Bryan Ratliff | Provost | 390796.8848 | Yes
25000 - Faculty Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 25005.8466 | No
26000 - Enrollment Affairs: Office of the Vice Provost | Jennifer Gourley | Provost | 51044.6471 | No
27000 - Research: Office of the Vice Provost | Jennifer Bischoff | Provost | 99496.1759 | No
28000 - Undergraduate Affairs and Residential Faculty: Office of the Vice Provost | Jennifer Bischoff | Provost | 15307.6474 | No
29100 - Housing: Assignments and Operations | Ashley Thompson | Provost | 2116760.1201 | No
30100 - Dean of Students: Office of the Dean | Lauren Kysar | Provost | 246476.6172 | No
30400 - Greek Life | Lauren Kysar | Provost | 131042.95 | No
31100 - Library System | Matthew McGlasson | Provost | 523095.4249 | No
35000 - Administration: Office of the Vice Chancellor | Ben Morse | Administration | 431.3202 | No
36000 - Business Services Administration | Ben Morse | Administration | 285287.7848 | No
37000 - Facilities: Office of the Chief Facilities Officer | Ally Sullivan | Administration | 106777.9002 | No
38000 - Human Resources: Office of the Chief Human Resources Officer | Ben Morse | Administration | 21719.5458 | No
39000 - Office of Chief Public Safety Officer | Dawn Radford | Administration | 21792.82 | No
40000 - Athletics: Office of the Vice Chancellor | Phillip Brown | Athletics | 493496.099 | No
40800 - Vanderbilt Recreation and Wellness Center | Phillip Brown | Athletics | 312213.46 | No
41000 - Communications: Office of the Vice Chancellor | Catherine Kozak | Communications | 672.1876 | No
42000 - Dev and Alumni Relations: Office of Vice Chancellor | Gena Cobble | Development and Alumni Relations | 1761.2529 | No
43000 - Equity, Diversity, and Inclusion: Office of the Vice Chancellor | Rachel Hansbrough | Equity, Diversity, and Inclusion | 22966.12 | No
44000 - Finance: Office of the Vice Chancellor | Lindsay Burgener | Finance | 26591.9412 | No
45000 - General Counsel: Office of the Vice Chancellor | Lizzie Shilliam | General Counsel | 0 | No
46000 - IT: Office of the Vice Chancellor | Heather Slagell | VUIT | 58330.7689 | No
47000 - Audit, Risk, and Advisory Services | Bruce Weisman | Audit, Risk, and Advisory | 2917.0407 | No
48000 - Investments: Office of the Vice Chancellor | Bart Bunk | Investments | 0 | No
49000 - Government and Community Relations: Office of the Vice Chancellor | Alex Shea | Government & Community Relations | 7838.8727 | No
63000 - Campus Initiatives | Kirk Stonecipher | Chancellor | 0 | No
7401519.3498

## Notes (hidden)
1. Review the proposed project list (attached) which now includes descriptions and capital versus operating designations.
2. Review procedures for shared buildings (ex: MRB III).
a. Facilities proposes that the majority / primary building owner bears the expense and receives the funds transfer.
3. Review procedures for operating expense facility renewal projects.
a. Facilities proposes that the building owner bears the expense and receives the funds transfer.
b. Schools should consider creating a unique intersection (program and/or activity) code to track opex project expenses discretly in Oracle. Account code 6405 will typically be used.
4. Discuss with Finance if we need to make any preparations to be set up for the funds transfers on July 1 from the schools to the Facility Renewal Program (FRP program code)
a. Per Kristy Stone the initial set of transfers will be a journal entry prepared by Facilities, approvals by each individual CBO are not required.